## Read Me
HR Department - Task Tracker (Living Document)
Snapshot built from WhatsApp exports on 2026-10-25. Deadline for all open items: 2026-11-10 (10 Nov 2026).
How to use
1. 'Master Task Log' = every instruction found in the HR WhatsApp chats (group + 1:1 with Rajendra Prasad + 1:1 with Gnaneshwar), with status and evidence.
2. 'Pending Action Items' = only the open items (PENDING / PARTIAL / VERIFY) sorted by priority - use this for weekly follow-up.
3. Update the 'Status' and 'Latest remark' columns in Master Task Log; the Pending tab is a filtered copy, so re-copy or filter the master when you review.
4. Add new instructions as new rows with the next ID in the category (A = Performance, B = ClickUp/Daily reports, C = Recruitment, D = Onboarding/Trusts, E = Payroll, F = Engagement, G = Policies, H = Employee cases).
5. Log every change in 'Change Log' (date, who, what changed).
6. ClickUp: open items are also created as tasks assigned to Gnaneshwar (Rajendra Prasad does not use ClickUp) in HR Department > 'MKCD Follow-up Action Items (WhatsApp) - Due 10 Nov 2026'.
Status legend
COMPLETED - evidence of completion in chat
PENDING - instruction given, no evidence of completion
PARTIAL - started / partly delivered, remainder open
VERIFY - probably done but no written confirmation; HR to confirm
RECURRING - standing process (daily / monthly); shown for R&R and routine checks
Owners
RP = Rajendra Prasad (HR Manager); GN = Gnaneshwar (HR Executive); BOTH = joint; MKCD = your own decision pending

## Master Task Log
ID | Category | Task / Instruction | Owner | Status | Priority | Source (chat & date) | Evidence / last update | Next action | Deadline | ClickUp task | Follow-up date | Latest remark (update here)
A1 | Performance & Daily Reporting | Daily Performance Report (Target vs Actual) for ALL 41 employees, by 11 AM every day; weekly, bi-weekly and monthly roll-ups; non-achievers in red; include late logins, unplanned leaves, mistakes; seniors included. | Gnaneshwar (HR Executive) | PARTIAL | URGENT | Group 12 May 2026; Gnaneshwar 1:1 14 Oct 2026 | Report started (previous-day format approved 23 Sep). 14 Oct report covered only 30 employees; MKCD: 'Total employees 41. I do not want any reasons.' Drivers to be covered via a register. Also ClickUp 14yp17znrwc (live performance dashboard). | Cover all 41 employees daily (drivers via register). Share as Google Sheet link + email every day by 11 AM. | 2026-11-10 | Yes
A2 | Performance & Daily Reporting | Measurable daily/weekly/monthly targets set in writing (email) for every employee by their reporting authority; each employee's targets + Roles & Responsibilities sent to them by email. | Rajendra Prasad + Gnaneshwar | PENDING | URGENT | Group 7 Oct 2025, 16 Feb 2026, 12 & 16 May 2026, 11 Oct 2026 | R&R mails done for some (ClickUp: telecaller R&R Jan 2026, all-employee R&R Jun 2026). Targets in writing still missing - MKCD on 11 Oct: 'No one should say I didn't know my target'. Also ClickUp 14yp17zk7xe (measurable targets for every role) and 14yp17zkpzz (departmental goals cascade). | Collect target sheet from every reporting authority (STDD, Sai Vardhan, Hem Chand, Satish, Nama Prabhu, Shravan) and email each employee their targets + R&R. Share consolidated sheet with MKCD. | 2026-11-10 | Yes
A3 | Performance & Daily Reporting | Half-yearly (Apr-Sep 2026) performance appraisal: form to all employees, filled and returned, review completed; October salary proportional to 6-month performance. | Rajendra Prasad + Gnaneshwar | PENDING | URGENT | Group 21 Oct 2026, 24 Oct 2026 | RP set employee deadline as Monday 27 Oct instead of 22 Oct. MKCD: Gnaneshwar to call every employee and get all forms by Monday first half. | All forms in by 27 Oct 1 PM; review meetings scheduled with MKCD/STDD; results feed October payroll. | 2026-11-10 | Yes
A4 | Performance & Daily Reporting | Written performance summary per employee for last 6 months in a simple format: employee, month-on-month result, targets achieved / not achieved, % achieved - plus the same for last FY, plus a separate October 2026 performance report. | Rajendra Prasad + Gnaneshwar | PENDING | URGENT | Group 12 May 2026 (last FY report), 24 Oct 2026 | MKCD on 24 Oct: 'I did not get this for last year also, so this is a very, very crucial document.' | Deliver 3 sheets: (1) Apr-Sep 2026, (2) FY 2025-26, (3) Oct 2026 - in Google Sheet by 10 Nov. | 2026-11-10 | Yes
A5 | Performance & Daily Reporting | Adopt a performance-appraisal software (Keka or any standard tool) so appraisal data is captured in a system, not in Word/Excel. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Group 6 Mar 2026, 24 Oct 2026 | No tool selected. MKCD: 'there are so many softwares... please try to use any one of them'. | Evaluate Keka Performance module (already a Keka customer) vs Zoho People; present recommendation + cost to MKCD. | 2026-11-10 | Yes
A6 | Performance & Daily Reporting | Monthly performance appraisal for every employee; salary paid in proportion to target achievement; compile monthly data for yearly appraisal (promotion / increment / termination). | Rajendra Prasad (HR Manager) | RECURRING | HIGH | Group 22 Mar, 3 May, 11 Oct 2026 | Policy stated repeatedly; telecaller proportional pay applied partly (Apr-May). Not yet systematic for all employees. Also ClickUp 14yp17zmem1 (performance-linked pay one-to-one). | Make it part of monthly payroll checklist from October 2026 payroll onwards. | Monthly / ongoing | Yes
A7 | Performance & Daily Reporting | Monthly late-login / LOP analysis report (Keka grace 10:05, 3 lates = half-day LOP). Exceptions only with MKCD email approval - same rule for all. | Gnaneshwar (HR Executive) | RECURRING | NORMAL | Group 12 May 2026 | April 2026 late-comers report delivered 12 May. MKCD: from today no exception without email approval. | Send every month with payroll; list any exception approvals attached. | Monthly / ongoing
A8 | Performance & Daily Reporting | Daily login / logout time of every team member to MKCD for 10 days (pattern check of late login / early logout). | Gnaneshwar (HR Executive) | VERIFY | NORMAL | Group 12 May 2026 | Gnaneshwar: 'Noted, I will share accordingly.' No delivery seen in chat. | Confirm whether the 10-day log was sent; if not, send Oct 13-24 login/logout data now. | 2026-11-10 | Yes
B1 | ClickUp & Daily Report Discipline | Every employee sends a Daily Report email with ClickUp / Tata Tele screenshot showing all 8.5 hours (no essays, no Excel). Non-compliance = LOP / 0.5-day penalty. Drivers via register. | Rajendra Prasad + Gnaneshwar | PENDING | URGENT | Group 26 Jun, 24 Aug, 11 Oct, 12 Oct, 23 Oct 2026 | 'More than 10 reminders' per MKCD (23 Oct). Gnaneshwar proposed 0.5-day penalty per miss (12 Oct). Still many employees not using software (23 Oct). Also ClickUp 14yp17zk7xf (ClickUp time tracking mandatory). | Issue written circular (email) on penalty rule; from 27 Oct mark LOP without exception; weekly compliance list to MKCD. | 2026-11-10 | Yes
B2 | ClickUp & Daily Report Discipline | Non-compliance report: employees who did NOT send daily report email / did NOT capture 8.5 hrs in ClickUp - with reason and penalty imposed - for 1-12 Oct, then September, then August. Send by EMAIL (not only sheet). | Gnaneshwar (HR Executive) | PARTIAL | URGENT | Group 12 Oct 2026; Gnaneshwar 1:1 14 Oct 2026 | 1-12 Oct sheet shared 14 Oct but only 30 employees and no email; Sept and Aug not started. | Redo 1-12 Oct for 41 employees with penalty column; complete September and August; email all three. | 2026-11-10 | Yes
B3 | ClickUp & Daily Report Discipline | Sai Vardhan told Arjun 'no need to use ClickUp' and is not using it himself - against org policy. Take action and inform everyone that policy is mandatory for all. | Rajendra Prasad (HR Manager) | PENDING | URGENT | Group 24 Oct 2026 | MKCD: 'Everyone can't decide on their own.' | Written communication to Sai Vardhan & Arjun; confirm both are logging in ClickUp from 27 Oct; report to MKCD. | 2026-11-10 | Yes
B4 | ClickUp & Daily Report Discipline | Help whole team work in ClickUp - Hem Chand to create users and train; buy extra ClickUp / Tally seats if needed; telecaller call minutes from Tata Tele software only. | Gnaneshwar (HR Executive) | PARTIAL | HIGH | Group 24 Aug, 26 Jun, 23 Oct 2026 | Gnaneshwar task 'ClickUp and Tata Tele usage report' in progress (ClickUp 24 Oct). | List employees without ClickUp seat / not logging; get seats added; send usage report weekly. | 2026-11-10 | Yes
B5 | ClickUp & Daily Report Discipline | Try Truein AI time-capture tool for attendance. | Gnaneshwar (HR Executive) | VERIFY | LOW | Group 22 May 2026 | 'Noted Prabhu.' No follow-up. | Confirm whether trial was done; share 3-line finding. | 2026-11-10 | Yes
B6 | ClickUp & Daily Report Discipline | Inform all employees to join Slack by EOD. | Gnaneshwar (HR Executive) | COMPLETED | LOW | Gnaneshwar 1:1 11 Sep 2026 | Done 11 Sep.
B7 | ClickUp & Daily Report Discipline | Remote login access for Bala Mukunda Dasa. | Gnaneshwar (HR Executive) | COMPLETED | LOW | Group 10 Sep 2026 | Provided same day.
B8 | ClickUp & Daily Report Discipline | Biometric thumb access to 1st floor for Kirtaniyas, Bala Mukunda Dasa, MKCD and everyone missing. | Gnaneshwar (HR Executive) | COMPLETED | NORMAL | Group 17 Sep 2026 | Gnaneshwar: 'tomorrow I will provide access'. ClickUp task 14yp17zxpg9 marked complete by Gnaneshwar on 27 Oct 2026. | Confirm all staff enrolled; maintain access list. |  | Yes
C1 | Recruitment | Recruit a go-getter Tele Sales Manager (fund-raising / NGO tele-sales background) to run the telecaller team. | Rajendra Prasad (HR Manager) | PARTIAL | HIGH | Group 22 Nov 2025, 14 Mar, 16 May 2026 | P Srilakshmi Sailaja onboarded Aug 2026 as Telesales Manager - WFH, Rs 30K fixed for 3 months, review after 3 months (Nov 2026). | 3-month review due Nov 2026: performance data, decision on continuation / full-time role. | 2026-11-10 | Yes
C2 | Recruitment | Recruit Digital Marketing Manager. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Group 16 May 2026 | MKCD asked for update; none given. | Status update: JD, postings, pipeline, shortlist date. | 2026-11-10 | Yes
C3 | Recruitment | Recruit Best PPC Expert (10+ years, high package acceptable). | Rajendra Prasad (HR Manager) | PENDING | HIGH | Group 21 May 2026 | 'We will look into this.' ClickUp 'PPC Recruitment' in progress since Mar 2026. | Status update with shortlisted profiles. | 2026-11-10 | Yes
C4 | Recruitment | Recruit CSR Executive / Business Development Executive / Advertisement-seva sales (top priority roles listed Dec 2025). | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Group 30 Aug 2025, 7 Dec 2025 | ClickUp 'CSR Executive Recruitment' in progress since Dec 2025; no hire. Also ClickUp 14yp17zmepb (BDM recruitment). | Status update; decide continue / close requisition. | 2026-11-10 | Yes
C5 | Recruitment | Executive Assistant / Executive Secretary for MKCD (experience as EA to a CXO); Rahul Bajaj profile (donor referral) to be met and opinion shared. | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Group 5 Oct 2025, 20 May 2026 | RP: 'I will call him & meet him. Then share my opinion.' No update. | Share outcome of Rahul Bajaj discussion; if closed, restart search. | 2026-11-10 | Yes
C6 | Recruitment | Mandatory 4-round interview process (HR -> Shruthadev Prabhu -> Maha Bhuja Prabhu -> MKCD) + email per candidate with each round's feedback (subject: Position - Candidate - Date). Inform MKCD & STDD before any offer letter is issued. | Rajendra Prasad (HR Manager) | RECURRING | HIGH | Group 15 Oct 2025, 11 Jan, 14 Mar, 7 May 2026, 19-21 Oct 2026 | Lapses: Sumanth (SEO) hired without MKCD/STDD interview (May); 3-4 recent WFH appointments without informing STDD (19 Oct). RP agreed to fill gaps (21 Oct). | Written SOP circulated; no offer letter without MKCD/STDD sign-off email. | Monthly / ongoing | Yes
C7 | Recruitment | Use Keka Hiring module (paid Rs 29,370 on 7 May 2026) for end-to-end recruitment tracking incl. interview rounds and historical data. | Rajendra Prasad + Gnaneshwar | VERIFY | NORMAL | Group 10 Mar, 7 May 2026 | Payment done; RP: 'within a week we can start using'. Usage not confirmed. | Confirm module is live; all open positions and candidates entered; share screenshot. | 2026-11-10 | Yes
C8 | Recruitment | Aptitude / psychometric / English tests for all new candidates; share test details used so far. | Rajendra Prasad (HR Manager) | PENDING | LOW | Group 21 Oct 2025; ClickUp list 'Rajendra Prasad' | RP: 'I will check & share my feedback.' ClickUp item still 'to do'. | Finalise test set and add to the 4-round SOP. | 2026-11-10 | Yes
C9 | Recruitment | Solution to stop new hires leaving right after first salary (bond rejected by RP) - propose alternative (notice-period clause, salary-hold, probation terms). | Rajendra Prasad (HR Manager) | PENDING | LOW | Group 4 & 7 Dec 2025 | MKCD: 'Then what is the solution...?' - no answer. | Written proposal to MKCD. | 2026-11-10 | Yes
C10 | Recruitment | Work-from-home Mathaji telecaller team (Krishna-conscious ladies): Sailaja (done), G Swapna (offer 17 Oct), Vyshnavi, Malleswari, Bhavani profiles. | Rajendra Prasad + Gnaneshwar | PARTIAL | NORMAL | Group 21 Jul, 11 Aug, 8 Sep, 29 Sep, 17 Oct 2026 | Sailaja + Swapna onboarded; others screened. Gnaneshwar's daily tasks show WFH telecaller sourcing ongoing. | Pipeline status + performance tracking (calls/minutes/donations) for WFH callers; inform STDD/MKCD before each offer. | 2026-11-10 | Yes
C11 | Recruitment | Bangalore (RGI JP Nagar) telecaller - English + Kannada, two-wheeler. | Rajendra Prasad (HR Manager) | COMPLETED | LOW | Rajendra 1:1 19 Aug - 3 Oct 2026 | Deva Reddy joined; trained in Hyderabad 29 Sep; left for Bangalore 3 Oct. 25 Oct: MKCD directs closure of the Bengaluru office and this position - see I10.
C12 | Recruitment | ERP / Frappe developer for Yatra Dept. | Rajendra Prasad + Gnaneshwar | COMPLETED | LOW | Group 17-23 Apr 2026 | Sai Kumar Dumpeti hired (CTC 7.8L).
C13 | Recruitment | Content Writer (male, full-time, 30K). | Rajendra Prasad (HR Manager) | COMPLETED | LOW | Group 4-16 Dec 2025 | Venu Gopal joined Dec 2025. 25 Oct: MKCD's view is to terminate Venugopal for low output - see I11.
C14 | Recruitment | SEO specialist. | Rajendra Prasad (HR Manager) | COMPLETED | LOW | Group 10 Mar - 7 May 2026 | Sumanth joined 6 May 2026 (process lapse noted under C6).
C15 | Recruitment | 3 video editor cum graphic designers within 1 week. | Rajendra Prasad (HR Manager) | PARTIAL | NORMAL | Group 29 Nov 2025 | 1 identified from ISKCON Attapur; later Revanth (Satish referral). Satish now wants graphic designer not video editor (20 Aug). | Confirm current open count with Satish/STDD and close. | 2026-11-10 | Yes
C16 | Recruitment | Evaluate Jayanti Achuta Narayan Rao (Accounts, referred by Bhanu Nitai Prabhu) and give feedback. | Rajendra Prasad (HR Manager) | VERIFY | LOW | Group 24 Sep 2026 | STDD said profile too senior; Bhanu Prabhu asked for full evaluation. | Close the loop with Bhanu Nitai Prabhu and STDD. | 2026-11-10 | Yes
D1 | Onboarding, Trusts & Statutory | Place every employee / consultant in the correct trust (HKM Hyd / HKM India / RGI / TSF) as per contribution; convert consultants to employees only after MKCD's trust-wise list. | Rajendra Prasad + Gnaneshwar | PARTIAL | HIGH | Group 7 Sep, 22 Sep, 22 Oct 2026 | 17 employees on RGI on-roll (22 Oct). MKCD preparing trust-wise list (Org Structure sheet Sep 2026 has 'New Trust from Oct 2026' column). Satish -> consultant on HKM Hyd (MKCD to confirm). Veda Vittama's wife -> trust TBD. Also ClickUp 14yp17zk7x4 (allocate each employee to a trust). | MKCD to share final trust-wise list; HR to execute transfers, offer letters, PF/ESI mapping by 10 Nov. | 2026-11-10 | Yes
D2 | Onboarding, Trusts & Statutory | Move Himanshu and Accountant Naveen V from TSF to another trust from 1 Oct 2026 (TSF has no operations). | Rajendra Prasad (HR Manager) | PARTIAL | NORMAL | Group 29 Sep, 10 Oct 2026 | Naveen V shifted to RGIL (email 10 Oct). Himanshu - no confirmation (org sheet suggests HKM India). 25 Oct: Himanshu move approved 12 Oct; payroll + PF paperwork pending - see J11. | Confirm Himanshu's transfer and effective date. | 2026-11-10 | Yes
D3 | Onboarding, Trusts & Statutory | RGI ESI & PF registration. | Rajendra Prasad (HR Manager) | COMPLETED | LOW | Group 16-27 Apr, 12 Aug, 7 Sep 2026 | 'We have registered for ESI & PF' (7 Sep).
D4 | Onboarding, Trusts & Statutory | Transfer all TSF employees to HKM Hyd / HKM India / RGI with new appointment letters (effective 1 Jan 2026). | Rajendra Prasad + Gnaneshwar | COMPLETED | LOW | Group 11 Jan - 10 Feb 2026 | All onboarded by 10 Feb except Nandlal (not to be onboarded).
D5 | Onboarding, Trusts & Statutory | Share copies of all RGI appointment letters with MKCD, including MKCD's own appointment letter. | Rajendra Prasad (HR Manager) | VERIFY | NORMAL | Group 9 Feb 2026 | MKCD: 'share me the copies... even in my name one appointment letter should be there, I have not yet received'. No confirmation. | Share folder link with all RGI appointment letters. | 2026-11-10 | Yes
D6 | Onboarding, Trusts & Statutory | All employees' personal documents (Aadhaar, PAN, blood group, emergency contacts) in a Google Drive folder, link shared with MKCD. | Rajendra Prasad + Gnaneshwar | VERIFY | NORMAL | Group 22 & 26 Oct 2025 | RP: 'once collected fully, will be shared on Google Drive'. Link never seen in chat. | Share Drive folder link; keep updated for every new joiner. | 2026-11-10 | Yes
D7 | Onboarding, Trusts & Statutory | Employee Master Data + monthly & yearly CTC of ALL employees (on-roll and consultants) in a Google Sheet, updated on every joining / exit / revision; for budgeting. | Gnaneshwar (HR Executive) | RECURRING | HIGH | Group 16 May, 20 Aug, 25 Aug 2026; Gnaneshwar 1:1 7 Aug 2026 | CTC file delivered as Excel on 20 & 25 Aug. MKCD prefers Google Sheet links ('always send me in Google Sheet or email attachment'). | Keep one live Google Sheet; share link once; update within 1 day of any change. | Monthly / ongoing | Yes
D8 | Onboarding, Trusts & Statutory | Employee contact master (mobile, alternate, 2 emergency contacts, permanent address, official/personal emails). | Gnaneshwar (HR Executive) | COMPLETED | LOW | Gnaneshwar 1:1 12-14 Nov 2025, 14 Jul 2026 | Updated sheet shared 14 Jul 2026.
D9 | Onboarding, Trusts & Statutory | ID cards for all employees who do not have one (needed for festival duty). | Gnaneshwar (HR Executive) | VERIFY | LOW | Group 25 Aug 2026 | 'Noted sir.' No completion update. | Confirm list and issuance. | 2026-11-10 | Yes
D10 | Onboarding, Trusts & Statutory | RGIL email IDs for all staff (Hem Chand to create). | Gnaneshwar (HR Executive) | VERIFY | LOW | Rajendra 1:1 29 Aug 2026 | MKCD told Hem Chand to create for all staff. No confirmation. | Confirm creation and share ID list. | 2026-11-10 | Yes
D11 | Onboarding, Trusts & Statutory | Medical insurance: addition / deletion list to insurer (Naveen waiting for TSF Narsingi confirmation). | Gnaneshwar (HR Executive) | VERIFY | NORMAL | Gnaneshwar 1:1 3 Jul 2026; ClickUp Payroll list | No closure seen. | Confirm policy renewed and all current employees covered. | 2026-11-10 | Yes
D12 | Onboarding, Trusts & Statutory | Onboard Sashikanta Sahoo's wife (Janusri) as Tele Caller on payroll - CTC 18-20K; trust to be confirmed by MKCD. | Rajendra Prasad + Gnaneshwar | PENDING | NORMAL | Rajendra 1:1 12 Aug 2026; Group 25 Aug 2026 | MKCD: 'she should be on-boarded on payroll as Tele Caller, CTC and trust I will confirm'. No further update. 25 Oct: MKCD prefers event-based consultant for Junjunu Mataji instead of full-time - see J10. | MKCD to confirm CTC & trust; HR to issue offer and onboard. | 2026-11-10 | Yes
D13 | Onboarding, Trusts & Statutory | Onboard Veda Vittama Dasa's wife as full-time salaried employee (trust to be confirmed by MKCD). | Rajendra Prasad + Gnaneshwar | PENDING | NORMAL | Rajendra 1:1 / Group 21-22 Oct 2026 | MKCD: 'this person also can be onboarded, I will check and update which trust'. | MKCD to confirm trust; HR to issue offer. | 2026-11-10 | Yes
D14 | Onboarding, Trusts & Statutory | Office systems requirement: Rajashekhar Reddy, Shiva Vara Prasad, Sudhakar need new systems; Sathish to return TSF Mac mini/monitor; follow up with others. | Gnaneshwar (HR Executive) | VERIFY | LOW | Gnaneshwar 1:1 20 Aug 2026 | MKCD: 'Yes'. No closure seen. | Confirm systems issued / TSF equipment returned. | 2026-11-10 | Yes
E1 | Payroll & Finance | Pay sheets for all trusts to MKCD by 4th of every month (salary processed by 5th); include incentives & variable pay; share monthly attendance with each employee before payroll. | Rajendra Prasad + Gnaneshwar | RECURRING | HIGH | Group 2 Feb, 3 Mar, 4 Aug, 31 Aug, 5 Sep 2026; Rajendra 1:1 7 Feb 2026 | Generally met; occasional delays. October 2026 payroll to be performance-based (A3). | October payroll: attach performance % per employee. | Monthly / ongoing
E2 | Payroll & Finance | Ratha Yatra 2026 expenses: collect ALL bills; deduct from salary where bills missing; final consolidated report in Google Sheet with all latest payments. | Gnaneshwar (HR Executive) | PARTIAL | NORMAL | Gnaneshwar 1:1 29 Jul - 18 Aug 2026 | Bill-status report shared 7-8 Aug (Excel). Sai Vardhan still had a few bills pending; final Google Sheet after 18 Aug payments not seen. | Share final Google Sheet; confirm Sai Vardhan bills closed or deducted. | 2026-11-10 | Yes
E3 | Payroll & Finance | Same-day invoice to R Naveen (Finance) for every expense paid by card / UPI (Naukri, Apna, Lokal, Keka, etc.). | Rajendra Prasad + Gnaneshwar | RECURRING | NORMAL | Group 7 May, 8 Aug, 9 Sep 2026 | Apna invoice shared 9 Sep same day. Keep practice. | Standing rule. | Monthly / ongoing
E4 | Payroll & Finance | Hem Chand variable pay Rs 50,000 approved - pay with September salary. | Rajendra Prasad (HR Manager) | VERIFY | NORMAL | Group 6 Oct 2026 | Approved by MKCD & STDD 6 Oct. Payment not confirmed in chat. | Confirm paid. | 2026-11-10 | Yes
E5 | Payroll & Finance | Arjun: recover Rs 10,000 advance (Dec 2025) before 5 Apr 2026; email on record about non-response and pending bills; salary hold until settlement. | Rajendra Prasad (HR Manager) | VERIFY | NORMAL | Group 4 Mar, 23 Mar, 26 Mar 2026 | RP 'Ok Prabhuji'. Arjun still unresponsive in Oct (13 Oct). No closure. | Confirm recovery and email trail. | 2026-11-10 | Yes
E6 | Payroll & Finance | Vineet Bulbule group (KMY batch): clear 100% pending payment; escalate via Shruthadev Prabhu if needed. | Rajendra Prasad (HR Manager) | VERIFY | NORMAL | Rajendra 1:1 25 Jun, 1 Jul, 7 Aug 2026 | RP tried twice (25 Jun); MKCD chased again 7 Aug. No closure. | Confirm with Accountant Naveen that balance is received; else escalate. | 2026-11-10 | Yes
E7 | Payroll & Finance | Varun: salary advance adjustment (35K advance; March salary 17.5K adjusted). | Rajendra Prasad (HR Manager) | COMPLETED | LOW | Group 20-31 Mar, 6 Jul 2026 | RP 6 Jul: 'All loan amount recovered'.
E8 | Payroll & Finance | Satish: attendance full till 19 Sep; leave 20-30 Sep adjusted from EL (mail to Achyuth); resignation accepted; now consultant - trust to be confirmed by MKCD (likely HKM Hyd). | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Gnaneshwar 1:1 28 Sep 2026; Rajendra 1:1 30 Sep, 22 Oct 2026 | MKCD: 'I will update after 2 days. Mostly Satish will be consultant in HKM Hyderabad trust'. Consultancy agreement and KT still open - see I2. | MKCD confirms trust; HR issues consultant agreement; confirm EL adjustment mail sent. | 2026-11-10 | Yes
E9 | Payroll & Finance | Terminate / proportionally pay non-performing telecallers & fund raisers after grace period; conclude with Shruthadev Prabhu. | Rajendra Prasad (HR Manager) | PARTIAL | HIGH | Group 4 & 27 Dec 2025, 18 Mar, 3 May, 7-8 Sep 2026 | RP 8 Sep: 'will sit with STDD and conclude'. Shashank & Sai Sharath terminated 17 Sep (org sheet). No written conclusion to MKCD. 25 Oct: October salary strictly proportionate to performance for all telecallers - see J8. | Send written list: who is retained / exited / on proportional pay, with data. | 2026-11-10 | Yes
E10 | Payroll & Finance | Sunday & holiday roster for the whole year (50% telecallers + 1 graphics person every Sunday), finalised monthly with staff. | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Group 20 Dec 2025, 10 Jan, 3 Mar 2026 | RP 3 Mar: 'spoke to 2 telecallers, will formalise'. Yearly roster never shared. | Share annual roster (Nov 2026 - Oct 2027) in Google Sheet. | 2026-11-10 | Yes
F1 | Engagement, Training & Culture | Extra Mile / Best Performer award: nominations by 10th, finalised by 14th, ceremony on 15th every month with data-backed performance review; Q2 (Jul-Sep) awards in 2nd week Oct. | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Group 14 Feb, 15 Apr, 12 May, 27 Sep 2026 | Held Mar, Apr, May. Q2 awards pending - MKCD wants performance report first (27 Sep). | Run Q2 awards once A4 report is ready; auto driver Venkatesh (14 yrs) to be recognised. | 2026-11-10 | Yes
F2 | Engagement, Training & Culture | Monthly team meeting + weekly snacks prasadam; gifts (smart watches, power banks) available with MKCD/MHBD. | Rajendra Prasad (HR Manager) | RECURRING | LOW | Group 17 Nov 2025, 12 May 2026 | Happening irregularly. | Fix calendar: 15th of every month. | Monthly / ongoing
F3 | Engagement, Training & Culture | 2-day team-building training for whole organisation + 1-day recap after a month (announced by RP 26 Jun). | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Group 26 Jun 2026 | Not scheduled. | Propose dates, trainer, agenda, budget. | 2026-11-10 | Yes
F4 | Engagement, Training & Culture | Watch APF HR symposium recording (Golden Habits, TAPF Way) and share notes of what can be implemented. | Rajendra Prasad + Gnaneshwar | VERIFY | LOW | Group 10 & 12 Jul 2026 | RP: 'Ok'. Notes not seen. | Send notes (1 page). | 2026-11-10 | Yes
F5 | Engagement, Training & Culture | Collect participant feedback on 28-29 Jun sales training (Arjun's feedback shared); keep feedback window open. | Rajendra Prasad (HR Manager) | VERIFY | LOW | Group 29 Jun 2026 | Not seen. | Share feedback summary. | 2026-11-10
F6 | Engagement, Training & Culture | Daily 10:00-10:30 spiritual program (bhajan, japa, Gita reading) with a dedicated person to start on time. | Rajendra Prasad (HR Manager) | COMPLETED | LOW | Group 11-12 Sep 2026 | Gnaneshwar's ClickUp shows daily 'Chanting & Bhagavat Gita session'.
F7 | Engagement, Training & Culture | Personal mobile phone restriction policy in office (lockers / deposit) - discuss with MKCD next week and implement soon. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Group 24 Oct 2026 | RP: 'Sure Prabhuji'. | Draft policy + meet MKCD week of 27 Oct. | 2026-11-10 | Yes
F8 | Engagement, Training & Culture | Office discipline items raised by MHBD (AC/lights left on, late logins with remote punch, long breaks, no daily reports) - HR to take strict action and close; Gnaneshwar to check both floors before leaving. | Rajendra Prasad + Gnaneshwar | RECURRING | NORMAL | Group 3 Aug 2026 | 'Noted'. No closure report. | Closing checklist daily; monthly discipline summary. | Monthly / ongoing | Yes
F9 | Engagement, Training & Culture | Sales training: record sessions, certificates of participation, mobiles away, notepads - standards for all future trainings. | Rajendra Prasad (HR Manager) | COMPLETED | LOW | Group 26-29 Jun 2026 | Training held 28-29 Jun; recording agreed with trainer.
G1 | Policies & Documents | Tour & Travel / Yatra employee allowance policy (Rs 750 food/day, official accommodation, 3AC train, medical via ESI/insurance, nothing else) - finalise, get approval and circulate to all Yatra employees. | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Group 11 Sep 2025, 5 Oct 2025, 30 Oct 2025 | v1 sent by email 29 Oct 2025; RP asked MKCD to review. Not confirmed as approved / circulated. | MKCD to approve; RP to circulate with acknowledgement from each Yatra employee before next yatra. | 2026-11-10 | Yes
G2 | Policies & Documents | Mobile recharge policy (decent calling + data pack). | Rajendra Prasad (HR Manager) | VERIFY | LOW | Group 5 Oct 2025 | RP said he will create. Not seen. | Share policy. | 2026-11-10 | Yes
G3 | Policies & Documents | Map each telecaller to 1-2 preachers for knowledge transfer. | Rajendra Prasad (HR Manager) | VERIFY | LOW | Group 17 Sep 2025 | MKCD: 'Please do mapping immediately'. No mapping shared. | Share mapping sheet (may be superseded by Sai Vardhan structure). | 2026-11-10 | Yes
G4 | Policies & Documents | Minutes of Meeting email after every management meeting (detailed, double-checked). | Rajendra Prasad (HR Manager) | RECURRING | LOW | Group 8 & 25 Oct 2025 | Expectation set; Otter summaries used since Sep 2026. | Standing rule. | Monthly / ongoing
G5 | Policies & Documents | Consolidated status of ALL tasks given via WhatsApp / email / meetings (file 'Tasks 2026 - Your Name') - and weekly pending-task update email to MKCD. | Rajendra Prasad + Gnaneshwar | PARTIAL | HIGH | Group 18 Aug 2025 ... 13 Mar 2026 (RP done 14 Mar); 22 Jun 2026 (GN); 26 May 2026 | RP delivered once (14 Mar 2026). GN's 22 Jun update not seen. This tracker now serves as the master list. | Update this tracker's Google Sheet every Monday; email MKCD the pending list. | 2026-11-10 | Yes
G6 | Policies & Documents | Certificate format for awards - finalise (printing for 1 year). | Rajendra Prasad (HR Manager) | VERIFY | LOW | Group 27 Feb - 2 Mar 2026 | MKCD: 'we'll finalise next week'. Not seen. | Confirm. | 2026-11-10
G7 | Policies & Documents | Performance review / appraisal / increment cycle every March-April; HR team available in 1st week of every month (no leave). | Rajendra Prasad (HR Manager) | RECURRING | LOW | Group 3 Dec 2025, 2 Apr 2026 | Policy acknowledged. | Standing rule. | Monthly / ongoing
H1 | Employee Cases | Shravan: unapproved leave till 15 Oct; dependents' (driver, Rajashekar, Charan) salaries on hold - explain seriousness and responsibility; also earlier 3 leaves in Sept (ask him to meet MKCD). | Rajendra Prasad (HR Manager) | PENDING | HIGH | Group 7 Oct 2026; Gnaneshwar 1:1 28 Sep 2026 | RP called twice, no response (7 Oct). No closure. 25 Oct: no October salary; lower package / different role on rejoining - see J3. | Report outcome of discussion with Shravan; attendance / salary decision. | 2026-11-10 | Yes
H2 | Employee Cases | Sachi: fixed office hours (11:00 or 11:30 start, 8.5 hrs), no Sundays, no late nights - communicate as final decision. | Rajendra Prasad (HR Manager) | VERIFY | NORMAL | Group 27 Sep 2026 | No confirmation. | Confirm communicated and followed. | 2026-11-10 | Yes
H3 | Employee Cases | Premroop Prabhu, Sudhakar, Sahoo - discussion with MKCD on 16 Oct; outcomes / actions to be recorded. | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Rajendra 1:1 16 Oct 2026 | Meeting held 16 Oct; no written outcome. 25 Oct decisions recorded in J4 (Prema Rupa), J7 (Sudhakar), J10 (Sashikanta). | Email summary of decisions and actions for each. | 2026-11-10 | Yes
H4 | Employee Cases | Vikas: WFH till he returns after Diwali - inform Sai Vardhan; also earlier counselling on physical presence and unplanned leaves. | Rajendra Prasad (HR Manager) | COMPLETED | LOW | Group 3 Jun, 15-16 Oct 2026 | RP: 'Ok I will inform Sai'. 25 Oct: did not attend in October - no October salary; see J2.
H5 | Employee Cases | Gnaneshwar's own salary discussion request (23 Sep) and Daily Performance Report meeting with MKCD + STDD + RP (18 Sep). | MKCD (your own action) | PENDING | NORMAL | Gnaneshwar 1:1 18 & 23 Sep 2026 | MKCD: 'not today'. Not scheduled. | MKCD to schedule 30-min slot. | 2026-11-10
I1 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Replacement for Lingala Sai Sharath (donation telecaller, last working day 31 Oct) and hand-over of his positive donor leads to Sai Vardhan / Sharavan. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc (25 Oct 2026) B2 | Hand-over requested 15 Oct; no replacement sourced yet. | RP: start sourcing; GN: collect lead hand-over sheet from Sharath before 31 Oct. | 2026-11-10 | Yes
I2 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Satish Maddela consultancy agreement (Mondays on site; movie-editing scope, fee, IP) - pending with HR since 24 Oct. STDD to negotiate Rs 25,000/month (Rs 50,000 asked for 1-2 days a month is too costly); else end. October payment on hold. Satish -> Praveen knowledge transfer and documentation. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc B3 + G2; ClickUp 14yp17zk7xa / 14yp17zk7x9 / 14yp17zk7x6 | Agreement not drafted. Graphics lead role formally with Praveen meanwhile. | RP: draft agreement at the negotiated fee or issue closure letter; confirm KT completed. | 2026-11-10 | Yes
I3 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Social-media executive vacancy (Akhil left 17 Oct) - now covered by Venkatesh (PPC). MKCD to decide whether to still hire; HR to close or open the requisition accordingly. Akhil PIP task in ClickUp is obsolete - close it. | MKCD (your own action) | PENDING | NORMAL | Claude Action Items doc B4 / A5; ClickUp 14yp17zmenz (Akhil PIP) | Sep-2026 plan listed a Social Media Manager. | MKCD decision by 15 Nov; GN to close ClickUp task 14yp17zmenz. | 2026-11-10 | Yes
I4 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Roster integrity: confirm employment status of Anji (auto driver), P Ravi Kumar, Vinod Singh Thakur and the holder of the MKCP Assistant desk account (missing from the 24 Oct HR roster); also add Junjunu Mataji and Radha Giridhari records (paid but not in roster). P Ravi Kumar responsibilities / KT and the 2 pm meeting with HR to be concluded. | Gnaneshwar (HR Executive) | PENDING | HIGH | Claude Action Items doc B6, G14, G16; ClickUp 14yp17zmep3 / 14yp17zmep2 | Roster of 42 rows (24 Oct) excludes these names. | GN: reconcile roster vs pay sheets of all trusts; one row per paid person. | 2026-11-10 | Yes
I5 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Settle department placement of Sashikanta Sahoo, Prema Rupa Dasa, Sonayla Sudhakar, Yankiral Shiv Raj, Purushottam Sharma, P Srilakshmi Sailaja, Gaddam Sai Kiran (sources disagree); record accountant V Naveen Kumar as Yatra dept (TRIDAS/TSF accounts) or Hanuma's transfer to Yatra once HG LKP agrees. Then update master roster, Whimsical org board and department docs. | Rajendra Prasad + Gnaneshwar | PENDING | NORMAL | Claude Action Items doc B7, A1 | MKCD + STDD decision pending (due 7 Nov). | RP: prepare the placement sheet with recommendation for MKCD/STDD; GN: update roster/docs after decision. | 2026-11-10 | Yes
I6 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Collect dates of joining for all staff from Keka / GreytHR into the employee living documents (only 4 confirmed) and link every employee living doc from the Notion Leadership Hub and the HR roster sheet. | Gnaneshwar (HR Executive) | PENDING | LOW | Claude Action Items doc B8, D3 | Not started. | GN: export DOJ list from Keka; add to each doc; add links column in roster sheet. | 2026-11-10 | Yes
I7 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Daily-report & ClickUp compliance specifics: Nama Prabhu Dasa, Bala Mukunda Dasa, Banusundar irregular; Sai Vardhan to start ClickUp from 1 Nov; Revanth, Amit Mondal, Madhu Mangal, Hanumaya, Ramesh J, Purushottam, Chenna Reddy have no ClickUp / email (licence shortage) - buy licences or assign manager-maintained logs. ClickUp time tracking mandatory for all employees. | Gnaneshwar (HR Executive) | PENDING | HIGH | Claude Action Items doc B9; ClickUp 14yp17zk7xf | Licence shortage unresolved; see B2/B4. | GN: licence count and cost to MKCD by 7 Nov; confirm Sai Vardhan live on ClickUp 1 Nov. | 2026-11-10 | Yes
I8 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Decide which HR notes (performance flags) stay in the shared employee living documents vs a private HR tab. | MKCD (your own action) | PENDING | NORMAL | Claude Action Items doc B10 | Docs are shareable; performance notes currently inside them. | MKCD decision; RP to then move confidential notes. | 2026-11-10
I9 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | 2026-27 recruitment plan (approx. 45 roles, approx. Rs 17.2 L/month) - re-prioritise against the budget; sequence: CSR BD manager + proposal writer, AI core team, yatra coordinators. Finalise manpower requirements per department. Tech / AI hiring (GenAI engineer, Platform lead, Data scientist, backend developer): JDs from SRRD, compensation range approval, posting, sourcing - hold until MKCD confirms priority. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc B11; ClickUp 14yp17zp5xt / 5xr / 5xq / 5xp, 14yp17znrz3 / znrz1 / znryz, 14yp17zkq26 / zkq1q / zkq1r, 14yp17zmen3 / zmen2, 14yp17zmepa (CA-level accountant), MOM 86d3febu0 | Several duplicate hiring tasks open across ClickUp spaces; none progressing. | RP: one consolidated hiring plan sheet (role, trust, CTC, priority, status) to MKCD by 10 Nov; GN: link/merge duplicate ClickUp tasks. | 2026-11-10 | Yes
I10 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Close the Bengaluru office and the Bengaluru telecaller position (Deva Reddy): exit date, notice, asset return, lead hand-over; update Deva Reddy's doc and the Tele-sales dept doc. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc A4 (with HG LKP) | Decision direction given 25 Oct; reverses recruitment item C11. | RP: exit plan and notice draft for MKCD approval by 15 Nov. | 2026-11-10 | Yes
I11 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Kanukuntla Venugopal (content writer): MKCD's view is terminate for low output (content to be AI-generated; postings moved to Venkatesh). HR to follow due process - performance record, notice. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc A5 / G3 | In progress; not yet communicated to Venugopal. | RP: performance record + notice draft; conclude with STDD. | 2026-11-10 | Yes
I12 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Org structure, department structure and a written role / designation / JD / CTC document for every person (PID39-42); lean team target <= Rs 5 lakh/month; review web developer role at Rs 46k; department SPOC / role register; employee capability & responsibility matrix; communicate the new structure to all staff. Oct-Dec 2026 deliverable in the People & Operations plan. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Notion 'People & Operations (Vertical Plan)'; ClickUp 14yp17zmek9, 14yp17zmeke, 14yp17zp7pf, 14yp17zk7xj, 14yp17zkpzz; MASTER register MA-00165 | Dept R&R doc and employee living docs exist (Claude Docs, 24 Oct) - JDs/CTC not yet in them. | RP: fill designation, JD and CTC for every person in the living docs; GN: capability matrix sheet. | 2026-11-10 | Yes
I13 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Backup employee for every role with knowledge-transfer plan (PID101); second-line names to confirm (Tele-sales, Yatra coordinator, ERP, accounts lead). | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Notion People & Operations plan PID101; Claude Action Items doc B12 | Not started. | RP: backup column in the roster sheet, confirmed with each department head. | 2026-11-10 | Yes
I14 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | End-to-end recruitment & onboarding SOP and onboarding kit (PID102); quarterly training calendar with in-house and external speakers (PID15/16, Jan-Mar 2027); written R&R for Culture Connect; incorporate the GM/AVP promotion qualifying-criteria resolution into a formal promotion policy; re-recruit trained ex-employees under stricter SOPs where suitable. | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Notion People & Operations plan; ClickUp 14yp17znrx6; MASTER register MA-02102, MA-01735 | Planning stage. | RP: SOP + promotion policy drafts to MKCD by 10 Nov; training calendar by Dec. | 2026-11-10 | Yes
I15 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Employee monitoring software (laptops PID13, field executives PID14): trial and disclosure decision. Move performance-review ownership from HR to Operations (decision) and build the live performance dashboard. | MKCD (your own action) | PENDING | NORMAL | ClickUp 14yp17zmepj, 14yp17znrwb, 14yp17znrwc; Notion PID13/14 | Decisions pending with MKCD. | MKCD decision; GN to run the trial once approved. | 2026-11-10 | Yes
I16 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Email all staff on office hours, Sunday working and discipline rules (after-hours / spiritual-course time is not office hours; report at 10 am). Puri staff pilgrimage dates to be fixed with HR Manager. Prasadam contamination complaint to be closed with HR Manager. | Rajendra Prasad (HR Manager) | PENDING | NORMAL | ClickUp 14yp17zmep1, 14yp17zp0mr, 14yp17zp0mk | Open in Arjun Prabhu / MKCP Assistant lists. | RP: one circular on hours & discipline; dates for Puri pilgrimage; complaint closure note. | 2026-11-10 | Yes
I17 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Verify and close stale HR tasks: Shashank termination notice (14yp17zmeny), TSF salary payments release (14yp17znrw1), PF withdrawal rules query from a kirtaniya (MASTER MA-00317), staff engagement planning review (MA-00919), volunteer details collection (MOM 86d3febpm). | Gnaneshwar (HR Executive) | VERIFY | LOW | ClickUp MKCP Assistant list; MOM lists; MASTER register | Status unknown; likely done or obsolete. | GN: confirm each and close in ClickUp with a one-line comment. | 2026-11-10 | Yes
J1 | J - October payroll & performance decisions (MKCD 25 Oct) | HR process: issue written warning emails for every non-performance / target-shortfall case (J2-J12) BEFORE the October payroll; keep copies in the employee files. Zero-performance employees: termination email to HR. | Rajendra Prasad (HR Manager) | PENDING | URGENT | Claude Action Items doc G27; ClickUp 14yp17zmem2 | Due 3 Nov 2026. | RP: warning letters out by 3 Nov; list of letters issued to MKCD. | 2026-11-10 | Yes
J2 | J - October payroll & performance decisions (MKCD 25 Oct) | Vikash Kumar (Senior Tele Sales Executive): flagged non-performer 4-5 months; did not attend in October - no October salary; on return salary proportionate to performance. Performance plan or exit. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc B1, G21 | Earlier: WFH till Diwali (see H4). | RP: apply in October pay sheet; written notice. | 2026-11-10 | Yes
J3 | J - October payroll & performance decisions (MKCD 25 Oct) | B Sharavan Kumar: no October salary (absent all month, no leave balance); on rejoining a lower package and different role for a few months. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc G10 (see H1) | Unapproved leave since early Oct. | RP: pay sheet entry + letter. | 2026-11-10 | Yes
J4 | J - October payroll & performance decisions (MKCD 25 Oct) | Prema Rupa Dasa: no October salary (no performance for approx. 2 years despite warnings); rejoin only in a new role at a revised lower CTC - perform or exit. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc G12 (with Suguna Radha DD; see H3) | Discussion with MKCD on 16 Oct. | RP: pay sheet entry + revised-role letter. | 2026-11-10 | Yes
J5 | J - October payroll & performance decisions (MKCD 25 Oct) | Purushottam Sharma: stop salary - 1-1.5 months' leave taken without approval despite written refusal; resumes only on rejoining. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc G25 |  | RP: pay sheet entry + letter. | 2026-11-10 | Yes
J6 | J - October payroll & performance decisions (MKCD 25 Oct) | Kouloju Sumanth (SEO): terminate - no performance for weeks/months, excessive leave, conduct. Hem Chand takes over SEO. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc G6 |  | RP: termination due process with Hem Chand; final settlement. | 2026-11-10 | Yes
J7 | J - October payroll & performance decisions (MKCD 25 Oct) | Written serious warnings: Hem Chand Tunga (targets not taken seriously; clear months-old pending tasks or salary cut), Sonayla Sudhakar (salary proportionate to performance from October), Nagella Banusundar / Arjuna Bandhu Dasa (no log-in/log-out, no ClickUp, tasks pending; report at 10 am; must do tele-sales; training-attendance issue), Radha Giridhari (October salary cut with warning; behaviour must change). | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc G5, G23, G20, G16; ClickUp 14yp17zp0mj |  | RP: four warning letters by 3 Nov; copies to MKCD. | 2026-11-10 | Yes
J8 | J - October payroll & performance decisions (MKCD 25 Oct) | October salary strictly proportionate to performance for all telecallers (G Sai Kiran, Sai Sharath, Anthati Sai Kumar, Narsing Rao, Charan Kumar, Shiva Vara Prasad, Rajashekhar Reddy) with written warnings for shortfalls; Byreddy Saivardhan Reddy to prove performance this month (100% salary cannot continue while the team under-performs); A Faneendra Chary salary proportionate to own and team results. | Rajendra Prasad (HR Manager) | PENDING | URGENT | Claude Action Items doc G24, G17, G18 (see E9) | Target vs actual data from Sai Vardhan needed. | RP + GN: October target-vs-actual per telecaller -> pay sheet by 4 Nov. | 2026-11-10 | Yes
J9 | J - October payroll & performance decisions (MKCD 25 Oct) | End consultant retainers of Aniket (DYGN Media) and Srinivas Mahankali immediately; redirect the cost to in-house full-time hires. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc G26 (with STDD) |  | RP: closure emails and final invoices; inform Finance. | 2026-11-10 | Yes
J10 | J - October payroll & performance decisions (MKCD 25 Oct) | Sashikanta Sahoo: fix R&R in writing (housekeeping, purchases/stores/warehouse, kirtan-training organisation, watering plants - weekly duties - plus daily fundraising / telecalling and family visits). Junjunu Mataji (his wife): solid roadmap or move to event-based consultant paid per event (preferred) - supersedes the full-time telecaller onboarding in D12. | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Claude Action Items doc G13, G14 (with Suguna Radha DD) |  | RP: written R&R letter for Sashikanta; consultant terms for Junjunu Mataji for MKCD approval. | 2026-11-10 | Yes
J11 | J - October payroll & performance decisions (MKCD 25 Oct) | Himanshu Bisoyi trust movement TSF -> HKM Hyderabad (approved 12 Oct): complete payroll and PF paperwork (no new budget). | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Claude Action Items doc B5 (see D2) |  | RP: new appointment letter + PF transfer with Finance by 31 Oct. | 2026-11-10 | Yes
J12 | J - October payroll & performance decisions (MKCD 25 Oct) | CONFIDENTIAL (MKCD + RP only): Gnaneshwar - termination for underperformance over many months to be discussed with HR Manager; document the performance record; confirm consistency with offer-letter terms and put in writing before the October payroll (5 Nov). | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc G1; Gnaneshwar living doc 25 Oct note | Not yet discussed with RP. | MKCD + RP meeting before 5 Nov. Deliberately NOT created in ClickUp. | 2026-11-10

## Pending Action Items
ID | Category | Task / Instruction | Owner | Status | Priority | Source (chat & date) | Evidence / last update | Next action | Deadline | ClickUp task | Follow-up date | Latest remark (update here)
A1 | Performance & Daily Reporting | Daily Performance Report (Target vs Actual) for ALL 41 employees, by 11 AM every day; weekly, bi-weekly and monthly roll-ups; non-achievers in red; include late logins, unplanned leaves, mistakes; seniors included. | Gnaneshwar (HR Executive) | PARTIAL | URGENT | Group 12 May 2026; Gnaneshwar 1:1 14 Oct 2026 | Report started (previous-day format approved 23 Sep). 14 Oct report covered only 30 employees; MKCD: 'Total employees 41. I do not want any reasons.' Drivers to be covered via a register. Also ClickUp 14yp17znrwc (live performance dashboard). | Cover all 41 employees daily (drivers via register). Share as Google Sheet link + email every day by 11 AM. | 2026-11-10 | Yes
A2 | Performance & Daily Reporting | Measurable daily/weekly/monthly targets set in writing (email) for every employee by their reporting authority; each employee's targets + Roles & Responsibilities sent to them by email. | Rajendra Prasad + Gnaneshwar | PENDING | URGENT | Group 7 Oct 2025, 16 Feb 2026, 12 & 16 May 2026, 11 Oct 2026 | R&R mails done for some (ClickUp: telecaller R&R Jan 2026, all-employee R&R Jun 2026). Targets in writing still missing - MKCD on 11 Oct: 'No one should say I didn't know my target'. Also ClickUp 14yp17zk7xe (measurable targets for every role) and 14yp17zkpzz (departmental goals cascade). | Collect target sheet from every reporting authority (STDD, Sai Vardhan, Hem Chand, Satish, Nama Prabhu, Shravan) and email each employee their targets + R&R. Share consolidated sheet with MKCD. | 2026-11-10 | Yes
A3 | Performance & Daily Reporting | Half-yearly (Apr-Sep 2026) performance appraisal: form to all employees, filled and returned, review completed; October salary proportional to 6-month performance. | Rajendra Prasad + Gnaneshwar | PENDING | URGENT | Group 21 Oct 2026, 24 Oct 2026 | RP set employee deadline as Monday 27 Oct instead of 22 Oct. MKCD: Gnaneshwar to call every employee and get all forms by Monday first half. | All forms in by 27 Oct 1 PM; review meetings scheduled with MKCD/STDD; results feed October payroll. | 2026-11-10 | Yes
A4 | Performance & Daily Reporting | Written performance summary per employee for last 6 months in a simple format: employee, month-on-month result, targets achieved / not achieved, % achieved - plus the same for last FY, plus a separate October 2026 performance report. | Rajendra Prasad + Gnaneshwar | PENDING | URGENT | Group 12 May 2026 (last FY report), 24 Oct 2026 | MKCD on 24 Oct: 'I did not get this for last year also, so this is a very, very crucial document.' | Deliver 3 sheets: (1) Apr-Sep 2026, (2) FY 2025-26, (3) Oct 2026 - in Google Sheet by 10 Nov. | 2026-11-10 | Yes
B1 | ClickUp & Daily Report Discipline | Every employee sends a Daily Report email with ClickUp / Tata Tele screenshot showing all 8.5 hours (no essays, no Excel). Non-compliance = LOP / 0.5-day penalty. Drivers via register. | Rajendra Prasad + Gnaneshwar | PENDING | URGENT | Group 26 Jun, 24 Aug, 11 Oct, 12 Oct, 23 Oct 2026 | 'More than 10 reminders' per MKCD (23 Oct). Gnaneshwar proposed 0.5-day penalty per miss (12 Oct). Still many employees not using software (23 Oct). Also ClickUp 14yp17zk7xf (ClickUp time tracking mandatory). | Issue written circular (email) on penalty rule; from 27 Oct mark LOP without exception; weekly compliance list to MKCD. | 2026-11-10 | Yes
B2 | ClickUp & Daily Report Discipline | Non-compliance report: employees who did NOT send daily report email / did NOT capture 8.5 hrs in ClickUp - with reason and penalty imposed - for 1-12 Oct, then September, then August. Send by EMAIL (not only sheet). | Gnaneshwar (HR Executive) | PARTIAL | URGENT | Group 12 Oct 2026; Gnaneshwar 1:1 14 Oct 2026 | 1-12 Oct sheet shared 14 Oct but only 30 employees and no email; Sept and Aug not started. | Redo 1-12 Oct for 41 employees with penalty column; complete September and August; email all three. | 2026-11-10 | Yes
B3 | ClickUp & Daily Report Discipline | Sai Vardhan told Arjun 'no need to use ClickUp' and is not using it himself - against org policy. Take action and inform everyone that policy is mandatory for all. | Rajendra Prasad (HR Manager) | PENDING | URGENT | Group 24 Oct 2026 | MKCD: 'Everyone can't decide on their own.' | Written communication to Sai Vardhan & Arjun; confirm both are logging in ClickUp from 27 Oct; report to MKCD. | 2026-11-10 | Yes
J1 | J - October payroll & performance decisions (MKCD 25 Oct) | HR process: issue written warning emails for every non-performance / target-shortfall case (J2-J12) BEFORE the October payroll; keep copies in the employee files. Zero-performance employees: termination email to HR. | Rajendra Prasad (HR Manager) | PENDING | URGENT | Claude Action Items doc G27; ClickUp 14yp17zmem2 | Due 3 Nov 2026. | RP: warning letters out by 3 Nov; list of letters issued to MKCD. | 2026-11-10 | Yes
J8 | J - October payroll & performance decisions (MKCD 25 Oct) | October salary strictly proportionate to performance for all telecallers (G Sai Kiran, Sai Sharath, Anthati Sai Kumar, Narsing Rao, Charan Kumar, Shiva Vara Prasad, Rajashekhar Reddy) with written warnings for shortfalls; Byreddy Saivardhan Reddy to prove performance this month (100% salary cannot continue while the team under-performs); A Faneendra Chary salary proportionate to own and team results. | Rajendra Prasad (HR Manager) | PENDING | URGENT | Claude Action Items doc G24, G17, G18 (see E9) | Target vs actual data from Sai Vardhan needed. | RP + GN: October target-vs-actual per telecaller -> pay sheet by 4 Nov. | 2026-11-10 | Yes
A5 | Performance & Daily Reporting | Adopt a performance-appraisal software (Keka or any standard tool) so appraisal data is captured in a system, not in Word/Excel. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Group 6 Mar 2026, 24 Oct 2026 | No tool selected. MKCD: 'there are so many softwares... please try to use any one of them'. | Evaluate Keka Performance module (already a Keka customer) vs Zoho People; present recommendation + cost to MKCD. | 2026-11-10 | Yes
B4 | ClickUp & Daily Report Discipline | Help whole team work in ClickUp - Hem Chand to create users and train; buy extra ClickUp / Tally seats if needed; telecaller call minutes from Tata Tele software only. | Gnaneshwar (HR Executive) | PARTIAL | HIGH | Group 24 Aug, 26 Jun, 23 Oct 2026 | Gnaneshwar task 'ClickUp and Tata Tele usage report' in progress (ClickUp 24 Oct). | List employees without ClickUp seat / not logging; get seats added; send usage report weekly. | 2026-11-10 | Yes
C1 | Recruitment | Recruit a go-getter Tele Sales Manager (fund-raising / NGO tele-sales background) to run the telecaller team. | Rajendra Prasad (HR Manager) | PARTIAL | HIGH | Group 22 Nov 2025, 14 Mar, 16 May 2026 | P Srilakshmi Sailaja onboarded Aug 2026 as Telesales Manager - WFH, Rs 30K fixed for 3 months, review after 3 months (Nov 2026). | 3-month review due Nov 2026: performance data, decision on continuation / full-time role. | 2026-11-10 | Yes
C2 | Recruitment | Recruit Digital Marketing Manager. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Group 16 May 2026 | MKCD asked for update; none given. | Status update: JD, postings, pipeline, shortlist date. | 2026-11-10 | Yes
C3 | Recruitment | Recruit Best PPC Expert (10+ years, high package acceptable). | Rajendra Prasad (HR Manager) | PENDING | HIGH | Group 21 May 2026 | 'We will look into this.' ClickUp 'PPC Recruitment' in progress since Mar 2026. | Status update with shortlisted profiles. | 2026-11-10 | Yes
D1 | Onboarding, Trusts & Statutory | Place every employee / consultant in the correct trust (HKM Hyd / HKM India / RGI / TSF) as per contribution; convert consultants to employees only after MKCD's trust-wise list. | Rajendra Prasad + Gnaneshwar | PARTIAL | HIGH | Group 7 Sep, 22 Sep, 22 Oct 2026 | 17 employees on RGI on-roll (22 Oct). MKCD preparing trust-wise list (Org Structure sheet Sep 2026 has 'New Trust from Oct 2026' column). Satish -> consultant on HKM Hyd (MKCD to confirm). Veda Vittama's wife -> trust TBD. Also ClickUp 14yp17zk7x4 (allocate each employee to a trust). | MKCD to share final trust-wise list; HR to execute transfers, offer letters, PF/ESI mapping by 10 Nov. | 2026-11-10 | Yes
E9 | Payroll & Finance | Terminate / proportionally pay non-performing telecallers & fund raisers after grace period; conclude with Shruthadev Prabhu. | Rajendra Prasad (HR Manager) | PARTIAL | HIGH | Group 4 & 27 Dec 2025, 18 Mar, 3 May, 7-8 Sep 2026 | RP 8 Sep: 'will sit with STDD and conclude'. Shashank & Sai Sharath terminated 17 Sep (org sheet). No written conclusion to MKCD. 25 Oct: October salary strictly proportionate to performance for all telecallers - see J8. | Send written list: who is retained / exited / on proportional pay, with data. | 2026-11-10 | Yes
F7 | Engagement, Training & Culture | Personal mobile phone restriction policy in office (lockers / deposit) - discuss with MKCD next week and implement soon. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Group 24 Oct 2026 | RP: 'Sure Prabhuji'. | Draft policy + meet MKCD week of 27 Oct. | 2026-11-10 | Yes
G5 | Policies & Documents | Consolidated status of ALL tasks given via WhatsApp / email / meetings (file 'Tasks 2026 - Your Name') - and weekly pending-task update email to MKCD. | Rajendra Prasad + Gnaneshwar | PARTIAL | HIGH | Group 18 Aug 2025 ... 13 Mar 2026 (RP done 14 Mar); 22 Jun 2026 (GN); 26 May 2026 | RP delivered once (14 Mar 2026). GN's 22 Jun update not seen. This tracker now serves as the master list. | Update this tracker's Google Sheet every Monday; email MKCD the pending list. | 2026-11-10 | Yes
H1 | Employee Cases | Shravan: unapproved leave till 15 Oct; dependents' (driver, Rajashekar, Charan) salaries on hold - explain seriousness and responsibility; also earlier 3 leaves in Sept (ask him to meet MKCD). | Rajendra Prasad (HR Manager) | PENDING | HIGH | Group 7 Oct 2026; Gnaneshwar 1:1 28 Sep 2026 | RP called twice, no response (7 Oct). No closure. 25 Oct: no October salary; lower package / different role on rejoining - see J3. | Report outcome of discussion with Shravan; attendance / salary decision. | 2026-11-10 | Yes
I1 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Replacement for Lingala Sai Sharath (donation telecaller, last working day 31 Oct) and hand-over of his positive donor leads to Sai Vardhan / Sharavan. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc (25 Oct 2026) B2 | Hand-over requested 15 Oct; no replacement sourced yet. | RP: start sourcing; GN: collect lead hand-over sheet from Sharath before 31 Oct. | 2026-11-10 | Yes
I10 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Close the Bengaluru office and the Bengaluru telecaller position (Deva Reddy): exit date, notice, asset return, lead hand-over; update Deva Reddy's doc and the Tele-sales dept doc. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc A4 (with HG LKP) | Decision direction given 25 Oct; reverses recruitment item C11. | RP: exit plan and notice draft for MKCD approval by 15 Nov. | 2026-11-10 | Yes
I11 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Kanukuntla Venugopal (content writer): MKCD's view is terminate for low output (content to be AI-generated; postings moved to Venkatesh). HR to follow due process - performance record, notice. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc A5 / G3 | In progress; not yet communicated to Venugopal. | RP: performance record + notice draft; conclude with STDD. | 2026-11-10 | Yes
I12 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Org structure, department structure and a written role / designation / JD / CTC document for every person (PID39-42); lean team target <= Rs 5 lakh/month; review web developer role at Rs 46k; department SPOC / role register; employee capability & responsibility matrix; communicate the new structure to all staff. Oct-Dec 2026 deliverable in the People & Operations plan. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Notion 'People & Operations (Vertical Plan)'; ClickUp 14yp17zmek9, 14yp17zmeke, 14yp17zp7pf, 14yp17zk7xj, 14yp17zkpzz; MASTER register MA-00165 | Dept R&R doc and employee living docs exist (Claude Docs, 24 Oct) - JDs/CTC not yet in them. | RP: fill designation, JD and CTC for every person in the living docs; GN: capability matrix sheet. | 2026-11-10 | Yes
I2 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Satish Maddela consultancy agreement (Mondays on site; movie-editing scope, fee, IP) - pending with HR since 24 Oct. STDD to negotiate Rs 25,000/month (Rs 50,000 asked for 1-2 days a month is too costly); else end. October payment on hold. Satish -> Praveen knowledge transfer and documentation. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc B3 + G2; ClickUp 14yp17zk7xa / 14yp17zk7x9 / 14yp17zk7x6 | Agreement not drafted. Graphics lead role formally with Praveen meanwhile. | RP: draft agreement at the negotiated fee or issue closure letter; confirm KT completed. | 2026-11-10 | Yes
I4 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Roster integrity: confirm employment status of Anji (auto driver), P Ravi Kumar, Vinod Singh Thakur and the holder of the MKCP Assistant desk account (missing from the 24 Oct HR roster); also add Junjunu Mataji and Radha Giridhari records (paid but not in roster). P Ravi Kumar responsibilities / KT and the 2 pm meeting with HR to be concluded. | Gnaneshwar (HR Executive) | PENDING | HIGH | Claude Action Items doc B6, G14, G16; ClickUp 14yp17zmep3 / 14yp17zmep2 | Roster of 42 rows (24 Oct) excludes these names. | GN: reconcile roster vs pay sheets of all trusts; one row per paid person. | 2026-11-10 | Yes
I7 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Daily-report & ClickUp compliance specifics: Nama Prabhu Dasa, Bala Mukunda Dasa, Banusundar irregular; Sai Vardhan to start ClickUp from 1 Nov; Revanth, Amit Mondal, Madhu Mangal, Hanumaya, Ramesh J, Purushottam, Chenna Reddy have no ClickUp / email (licence shortage) - buy licences or assign manager-maintained logs. ClickUp time tracking mandatory for all employees. | Gnaneshwar (HR Executive) | PENDING | HIGH | Claude Action Items doc B9; ClickUp 14yp17zk7xf | Licence shortage unresolved; see B2/B4. | GN: licence count and cost to MKCD by 7 Nov; confirm Sai Vardhan live on ClickUp 1 Nov. | 2026-11-10 | Yes
I9 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | 2026-27 recruitment plan (approx. 45 roles, approx. Rs 17.2 L/month) - re-prioritise against the budget; sequence: CSR BD manager + proposal writer, AI core team, yatra coordinators. Finalise manpower requirements per department. Tech / AI hiring (GenAI engineer, Platform lead, Data scientist, backend developer): JDs from SRRD, compensation range approval, posting, sourcing - hold until MKCD confirms priority. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc B11; ClickUp 14yp17zp5xt / 5xr / 5xq / 5xp, 14yp17znrz3 / znrz1 / znryz, 14yp17zkq26 / zkq1q / zkq1r, 14yp17zmen3 / zmen2, 14yp17zmepa (CA-level accountant), MOM 86d3febu0 | Several duplicate hiring tasks open across ClickUp spaces; none progressing. | RP: one consolidated hiring plan sheet (role, trust, CTC, priority, status) to MKCD by 10 Nov; GN: link/merge duplicate ClickUp tasks. | 2026-11-10 | Yes
J12 | J - October payroll & performance decisions (MKCD 25 Oct) | CONFIDENTIAL (MKCD + RP only): Gnaneshwar - termination for underperformance over many months to be discussed with HR Manager; document the performance record; confirm consistency with offer-letter terms and put in writing before the October payroll (5 Nov). | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc G1; Gnaneshwar living doc 25 Oct note | Not yet discussed with RP. | MKCD + RP meeting before 5 Nov. Deliberately NOT created in ClickUp. | 2026-11-10
J2 | J - October payroll & performance decisions (MKCD 25 Oct) | Vikash Kumar (Senior Tele Sales Executive): flagged non-performer 4-5 months; did not attend in October - no October salary; on return salary proportionate to performance. Performance plan or exit. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc B1, G21 | Earlier: WFH till Diwali (see H4). | RP: apply in October pay sheet; written notice. | 2026-11-10 | Yes
J3 | J - October payroll & performance decisions (MKCD 25 Oct) | B Sharavan Kumar: no October salary (absent all month, no leave balance); on rejoining a lower package and different role for a few months. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc G10 (see H1) | Unapproved leave since early Oct. | RP: pay sheet entry + letter. | 2026-11-10 | Yes
J4 | J - October payroll & performance decisions (MKCD 25 Oct) | Prema Rupa Dasa: no October salary (no performance for approx. 2 years despite warnings); rejoin only in a new role at a revised lower CTC - perform or exit. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc G12 (with Suguna Radha DD; see H3) | Discussion with MKCD on 16 Oct. | RP: pay sheet entry + revised-role letter. | 2026-11-10 | Yes
J5 | J - October payroll & performance decisions (MKCD 25 Oct) | Purushottam Sharma: stop salary - 1-1.5 months' leave taken without approval despite written refusal; resumes only on rejoining. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc G25 |  | RP: pay sheet entry + letter. | 2026-11-10 | Yes
J6 | J - October payroll & performance decisions (MKCD 25 Oct) | Kouloju Sumanth (SEO): terminate - no performance for weeks/months, excessive leave, conduct. Hem Chand takes over SEO. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc G6 |  | RP: termination due process with Hem Chand; final settlement. | 2026-11-10 | Yes
J7 | J - October payroll & performance decisions (MKCD 25 Oct) | Written serious warnings: Hem Chand Tunga (targets not taken seriously; clear months-old pending tasks or salary cut), Sonayla Sudhakar (salary proportionate to performance from October), Nagella Banusundar / Arjuna Bandhu Dasa (no log-in/log-out, no ClickUp, tasks pending; report at 10 am; must do tele-sales; training-attendance issue), Radha Giridhari (October salary cut with warning; behaviour must change). | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc G5, G23, G20, G16; ClickUp 14yp17zp0mj |  | RP: four warning letters by 3 Nov; copies to MKCD. | 2026-11-10 | Yes
J9 | J - October payroll & performance decisions (MKCD 25 Oct) | End consultant retainers of Aniket (DYGN Media) and Srinivas Mahankali immediately; redirect the cost to in-house full-time hires. | Rajendra Prasad (HR Manager) | PENDING | HIGH | Claude Action Items doc G26 (with STDD) |  | RP: closure emails and final invoices; inform Finance. | 2026-11-10 | Yes
A8 | Performance & Daily Reporting | Daily login / logout time of every team member to MKCD for 10 days (pattern check of late login / early logout). | Gnaneshwar (HR Executive) | VERIFY | NORMAL | Group 12 May 2026 | Gnaneshwar: 'Noted, I will share accordingly.' No delivery seen in chat. | Confirm whether the 10-day log was sent; if not, send Oct 13-24 login/logout data now. | 2026-11-10 | Yes
C10 | Recruitment | Work-from-home Mathaji telecaller team (Krishna-conscious ladies): Sailaja (done), G Swapna (offer 17 Oct), Vyshnavi, Malleswari, Bhavani profiles. | Rajendra Prasad + Gnaneshwar | PARTIAL | NORMAL | Group 21 Jul, 11 Aug, 8 Sep, 29 Sep, 17 Oct 2026 | Sailaja + Swapna onboarded; others screened. Gnaneshwar's daily tasks show WFH telecaller sourcing ongoing. | Pipeline status + performance tracking (calls/minutes/donations) for WFH callers; inform STDD/MKCD before each offer. | 2026-11-10 | Yes
C15 | Recruitment | 3 video editor cum graphic designers within 1 week. | Rajendra Prasad (HR Manager) | PARTIAL | NORMAL | Group 29 Nov 2025 | 1 identified from ISKCON Attapur; later Revanth (Satish referral). Satish now wants graphic designer not video editor (20 Aug). | Confirm current open count with Satish/STDD and close. | 2026-11-10 | Yes
C4 | Recruitment | Recruit CSR Executive / Business Development Executive / Advertisement-seva sales (top priority roles listed Dec 2025). | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Group 30 Aug 2025, 7 Dec 2025 | ClickUp 'CSR Executive Recruitment' in progress since Dec 2025; no hire. Also ClickUp 14yp17zmepb (BDM recruitment). | Status update; decide continue / close requisition. | 2026-11-10 | Yes
C5 | Recruitment | Executive Assistant / Executive Secretary for MKCD (experience as EA to a CXO); Rahul Bajaj profile (donor referral) to be met and opinion shared. | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Group 5 Oct 2025, 20 May 2026 | RP: 'I will call him & meet him. Then share my opinion.' No update. | Share outcome of Rahul Bajaj discussion; if closed, restart search. | 2026-11-10 | Yes
C7 | Recruitment | Use Keka Hiring module (paid Rs 29,370 on 7 May 2026) for end-to-end recruitment tracking incl. interview rounds and historical data. | Rajendra Prasad + Gnaneshwar | VERIFY | NORMAL | Group 10 Mar, 7 May 2026 | Payment done; RP: 'within a week we can start using'. Usage not confirmed. | Confirm module is live; all open positions and candidates entered; share screenshot. | 2026-11-10 | Yes
D11 | Onboarding, Trusts & Statutory | Medical insurance: addition / deletion list to insurer (Naveen waiting for TSF Narsingi confirmation). | Gnaneshwar (HR Executive) | VERIFY | NORMAL | Gnaneshwar 1:1 3 Jul 2026; ClickUp Payroll list | No closure seen. | Confirm policy renewed and all current employees covered. | 2026-11-10 | Yes
D12 | Onboarding, Trusts & Statutory | Onboard Sashikanta Sahoo's wife (Janusri) as Tele Caller on payroll - CTC 18-20K; trust to be confirmed by MKCD. | Rajendra Prasad + Gnaneshwar | PENDING | NORMAL | Rajendra 1:1 12 Aug 2026; Group 25 Aug 2026 | MKCD: 'she should be on-boarded on payroll as Tele Caller, CTC and trust I will confirm'. No further update. 25 Oct: MKCD prefers event-based consultant for Junjunu Mataji instead of full-time - see J10. | MKCD to confirm CTC & trust; HR to issue offer and onboard. | 2026-11-10 | Yes
D13 | Onboarding, Trusts & Statutory | Onboard Veda Vittama Dasa's wife as full-time salaried employee (trust to be confirmed by MKCD). | Rajendra Prasad + Gnaneshwar | PENDING | NORMAL | Rajendra 1:1 / Group 21-22 Oct 2026 | MKCD: 'this person also can be onboarded, I will check and update which trust'. | MKCD to confirm trust; HR to issue offer. | 2026-11-10 | Yes
D2 | Onboarding, Trusts & Statutory | Move Himanshu and Accountant Naveen V from TSF to another trust from 1 Oct 2026 (TSF has no operations). | Rajendra Prasad (HR Manager) | PARTIAL | NORMAL | Group 29 Sep, 10 Oct 2026 | Naveen V shifted to RGIL (email 10 Oct). Himanshu - no confirmation (org sheet suggests HKM India). 25 Oct: Himanshu move approved 12 Oct; payroll + PF paperwork pending - see J11. | Confirm Himanshu's transfer and effective date. | 2026-11-10 | Yes
D5 | Onboarding, Trusts & Statutory | Share copies of all RGI appointment letters with MKCD, including MKCD's own appointment letter. | Rajendra Prasad (HR Manager) | VERIFY | NORMAL | Group 9 Feb 2026 | MKCD: 'share me the copies... even in my name one appointment letter should be there, I have not yet received'. No confirmation. | Share folder link with all RGI appointment letters. | 2026-11-10 | Yes
D6 | Onboarding, Trusts & Statutory | All employees' personal documents (Aadhaar, PAN, blood group, emergency contacts) in a Google Drive folder, link shared with MKCD. | Rajendra Prasad + Gnaneshwar | VERIFY | NORMAL | Group 22 & 26 Oct 2025 | RP: 'once collected fully, will be shared on Google Drive'. Link never seen in chat. | Share Drive folder link; keep updated for every new joiner. | 2026-11-10 | Yes
E10 | Payroll & Finance | Sunday & holiday roster for the whole year (50% telecallers + 1 graphics person every Sunday), finalised monthly with staff. | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Group 20 Dec 2025, 10 Jan, 3 Mar 2026 | RP 3 Mar: 'spoke to 2 telecallers, will formalise'. Yearly roster never shared. | Share annual roster (Nov 2026 - Oct 2027) in Google Sheet. | 2026-11-10 | Yes
E2 | Payroll & Finance | Ratha Yatra 2026 expenses: collect ALL bills; deduct from salary where bills missing; final consolidated report in Google Sheet with all latest payments. | Gnaneshwar (HR Executive) | PARTIAL | NORMAL | Gnaneshwar 1:1 29 Jul - 18 Aug 2026 | Bill-status report shared 7-8 Aug (Excel). Sai Vardhan still had a few bills pending; final Google Sheet after 18 Aug payments not seen. | Share final Google Sheet; confirm Sai Vardhan bills closed or deducted. | 2026-11-10 | Yes
E4 | Payroll & Finance | Hem Chand variable pay Rs 50,000 approved - pay with September salary. | Rajendra Prasad (HR Manager) | VERIFY | NORMAL | Group 6 Oct 2026 | Approved by MKCD & STDD 6 Oct. Payment not confirmed in chat. | Confirm paid. | 2026-11-10 | Yes
E5 | Payroll & Finance | Arjun: recover Rs 10,000 advance (Dec 2025) before 5 Apr 2026; email on record about non-response and pending bills; salary hold until settlement. | Rajendra Prasad (HR Manager) | VERIFY | NORMAL | Group 4 Mar, 23 Mar, 26 Mar 2026 | RP 'Ok Prabhuji'. Arjun still unresponsive in Oct (13 Oct). No closure. | Confirm recovery and email trail. | 2026-11-10 | Yes
E6 | Payroll & Finance | Vineet Bulbule group (KMY batch): clear 100% pending payment; escalate via Shruthadev Prabhu if needed. | Rajendra Prasad (HR Manager) | VERIFY | NORMAL | Rajendra 1:1 25 Jun, 1 Jul, 7 Aug 2026 | RP tried twice (25 Jun); MKCD chased again 7 Aug. No closure. | Confirm with Accountant Naveen that balance is received; else escalate. | 2026-11-10 | Yes
E8 | Payroll & Finance | Satish: attendance full till 19 Sep; leave 20-30 Sep adjusted from EL (mail to Achyuth); resignation accepted; now consultant - trust to be confirmed by MKCD (likely HKM Hyd). | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Gnaneshwar 1:1 28 Sep 2026; Rajendra 1:1 30 Sep, 22 Oct 2026 | MKCD: 'I will update after 2 days. Mostly Satish will be consultant in HKM Hyderabad trust'. Consultancy agreement and KT still open - see I2. | MKCD confirms trust; HR issues consultant agreement; confirm EL adjustment mail sent. | 2026-11-10 | Yes
F1 | Engagement, Training & Culture | Extra Mile / Best Performer award: nominations by 10th, finalised by 14th, ceremony on 15th every month with data-backed performance review; Q2 (Jul-Sep) awards in 2nd week Oct. | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Group 14 Feb, 15 Apr, 12 May, 27 Sep 2026 | Held Mar, Apr, May. Q2 awards pending - MKCD wants performance report first (27 Sep). | Run Q2 awards once A4 report is ready; auto driver Venkatesh (14 yrs) to be recognised. | 2026-11-10 | Yes
F3 | Engagement, Training & Culture | 2-day team-building training for whole organisation + 1-day recap after a month (announced by RP 26 Jun). | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Group 26 Jun 2026 | Not scheduled. | Propose dates, trainer, agenda, budget. | 2026-11-10 | Yes
G1 | Policies & Documents | Tour & Travel / Yatra employee allowance policy (Rs 750 food/day, official accommodation, 3AC train, medical via ESI/insurance, nothing else) - finalise, get approval and circulate to all Yatra employees. | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Group 11 Sep 2025, 5 Oct 2025, 30 Oct 2025 | v1 sent by email 29 Oct 2025; RP asked MKCD to review. Not confirmed as approved / circulated. | MKCD to approve; RP to circulate with acknowledgement from each Yatra employee before next yatra. | 2026-11-10 | Yes
H2 | Employee Cases | Sachi: fixed office hours (11:00 or 11:30 start, 8.5 hrs), no Sundays, no late nights - communicate as final decision. | Rajendra Prasad (HR Manager) | VERIFY | NORMAL | Group 27 Sep 2026 | No confirmation. | Confirm communicated and followed. | 2026-11-10 | Yes
H3 | Employee Cases | Premroop Prabhu, Sudhakar, Sahoo - discussion with MKCD on 16 Oct; outcomes / actions to be recorded. | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Rajendra 1:1 16 Oct 2026 | Meeting held 16 Oct; no written outcome. 25 Oct decisions recorded in J4 (Prema Rupa), J7 (Sudhakar), J10 (Sashikanta). | Email summary of decisions and actions for each. | 2026-11-10 | Yes
H5 | Employee Cases | Gnaneshwar's own salary discussion request (23 Sep) and Daily Performance Report meeting with MKCD + STDD + RP (18 Sep). | MKCD (your own action) | PENDING | NORMAL | Gnaneshwar 1:1 18 & 23 Sep 2026 | MKCD: 'not today'. Not scheduled. | MKCD to schedule 30-min slot. | 2026-11-10
I13 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Backup employee for every role with knowledge-transfer plan (PID101); second-line names to confirm (Tele-sales, Yatra coordinator, ERP, accounts lead). | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Notion People & Operations plan PID101; Claude Action Items doc B12 | Not started. | RP: backup column in the roster sheet, confirmed with each department head. | 2026-11-10 | Yes
I14 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | End-to-end recruitment & onboarding SOP and onboarding kit (PID102); quarterly training calendar with in-house and external speakers (PID15/16, Jan-Mar 2027); written R&R for Culture Connect; incorporate the GM/AVP promotion qualifying-criteria resolution into a formal promotion policy; re-recruit trained ex-employees under stricter SOPs where suitable. | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Notion People & Operations plan; ClickUp 14yp17znrx6; MASTER register MA-02102, MA-01735 | Planning stage. | RP: SOP + promotion policy drafts to MKCD by 10 Nov; training calendar by Dec. | 2026-11-10 | Yes
I15 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Employee monitoring software (laptops PID13, field executives PID14): trial and disclosure decision. Move performance-review ownership from HR to Operations (decision) and build the live performance dashboard. | MKCD (your own action) | PENDING | NORMAL | ClickUp 14yp17zmepj, 14yp17znrwb, 14yp17znrwc; Notion PID13/14 | Decisions pending with MKCD. | MKCD decision; GN to run the trial once approved. | 2026-11-10 | Yes
I16 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Email all staff on office hours, Sunday working and discipline rules (after-hours / spiritual-course time is not office hours; report at 10 am). Puri staff pilgrimage dates to be fixed with HR Manager. Prasadam contamination complaint to be closed with HR Manager. | Rajendra Prasad (HR Manager) | PENDING | NORMAL | ClickUp 14yp17zmep1, 14yp17zp0mr, 14yp17zp0mk | Open in Arjun Prabhu / MKCP Assistant lists. | RP: one circular on hours & discipline; dates for Puri pilgrimage; complaint closure note. | 2026-11-10 | Yes
I3 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Social-media executive vacancy (Akhil left 17 Oct) - now covered by Venkatesh (PPC). MKCD to decide whether to still hire; HR to close or open the requisition accordingly. Akhil PIP task in ClickUp is obsolete - close it. | MKCD (your own action) | PENDING | NORMAL | Claude Action Items doc B4 / A5; ClickUp 14yp17zmenz (Akhil PIP) | Sep-2026 plan listed a Social Media Manager. | MKCD decision by 15 Nov; GN to close ClickUp task 14yp17zmenz. | 2026-11-10 | Yes
I5 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Settle department placement of Sashikanta Sahoo, Prema Rupa Dasa, Sonayla Sudhakar, Yankiral Shiv Raj, Purushottam Sharma, P Srilakshmi Sailaja, Gaddam Sai Kiran (sources disagree); record accountant V Naveen Kumar as Yatra dept (TRIDAS/TSF accounts) or Hanuma's transfer to Yatra once HG LKP agrees. Then update master roster, Whimsical org board and department docs. | Rajendra Prasad + Gnaneshwar | PENDING | NORMAL | Claude Action Items doc B7, A1 | MKCD + STDD decision pending (due 7 Nov). | RP: prepare the placement sheet with recommendation for MKCD/STDD; GN: update roster/docs after decision. | 2026-11-10 | Yes
I8 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Decide which HR notes (performance flags) stay in the shared employee living documents vs a private HR tab. | MKCD (your own action) | PENDING | NORMAL | Claude Action Items doc B10 | Docs are shareable; performance notes currently inside them. | MKCD decision; RP to then move confidential notes. | 2026-11-10
J10 | J - October payroll & performance decisions (MKCD 25 Oct) | Sashikanta Sahoo: fix R&R in writing (housekeeping, purchases/stores/warehouse, kirtan-training organisation, watering plants - weekly duties - plus daily fundraising / telecalling and family visits). Junjunu Mataji (his wife): solid roadmap or move to event-based consultant paid per event (preferred) - supersedes the full-time telecaller onboarding in D12. | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Claude Action Items doc G13, G14 (with Suguna Radha DD) |  | RP: written R&R letter for Sashikanta; consultant terms for Junjunu Mataji for MKCD approval. | 2026-11-10 | Yes
J11 | J - October payroll & performance decisions (MKCD 25 Oct) | Himanshu Bisoyi trust movement TSF -> HKM Hyderabad (approved 12 Oct): complete payroll and PF paperwork (no new budget). | Rajendra Prasad (HR Manager) | PENDING | NORMAL | Claude Action Items doc B5 (see D2) |  | RP: new appointment letter + PF transfer with Finance by 31 Oct. | 2026-11-10 | Yes
B5 | ClickUp & Daily Report Discipline | Try Truein AI time-capture tool for attendance. | Gnaneshwar (HR Executive) | VERIFY | LOW | Group 22 May 2026 | 'Noted Prabhu.' No follow-up. | Confirm whether trial was done; share 3-line finding. | 2026-11-10 | Yes
C16 | Recruitment | Evaluate Jayanti Achuta Narayan Rao (Accounts, referred by Bhanu Nitai Prabhu) and give feedback. | Rajendra Prasad (HR Manager) | VERIFY | LOW | Group 24 Sep 2026 | STDD said profile too senior; Bhanu Prabhu asked for full evaluation. | Close the loop with Bhanu Nitai Prabhu and STDD. | 2026-11-10 | Yes
C8 | Recruitment | Aptitude / psychometric / English tests for all new candidates; share test details used so far. | Rajendra Prasad (HR Manager) | PENDING | LOW | Group 21 Oct 2025; ClickUp list 'Rajendra Prasad' | RP: 'I will check & share my feedback.' ClickUp item still 'to do'. | Finalise test set and add to the 4-round SOP. | 2026-11-10 | Yes
C9 | Recruitment | Solution to stop new hires leaving right after first salary (bond rejected by RP) - propose alternative (notice-period clause, salary-hold, probation terms). | Rajendra Prasad (HR Manager) | PENDING | LOW | Group 4 & 7 Dec 2025 | MKCD: 'Then what is the solution...?' - no answer. | Written proposal to MKCD. | 2026-11-10 | Yes
D10 | Onboarding, Trusts & Statutory | RGIL email IDs for all staff (Hem Chand to create). | Gnaneshwar (HR Executive) | VERIFY | LOW | Rajendra 1:1 29 Aug 2026 | MKCD told Hem Chand to create for all staff. No confirmation. | Confirm creation and share ID list. | 2026-11-10 | Yes
D14 | Onboarding, Trusts & Statutory | Office systems requirement: Rajashekhar Reddy, Shiva Vara Prasad, Sudhakar need new systems; Sathish to return TSF Mac mini/monitor; follow up with others. | Gnaneshwar (HR Executive) | VERIFY | LOW | Gnaneshwar 1:1 20 Aug 2026 | MKCD: 'Yes'. No closure seen. | Confirm systems issued / TSF equipment returned. | 2026-11-10 | Yes
D9 | Onboarding, Trusts & Statutory | ID cards for all employees who do not have one (needed for festival duty). | Gnaneshwar (HR Executive) | VERIFY | LOW | Group 25 Aug 2026 | 'Noted sir.' No completion update. | Confirm list and issuance. | 2026-11-10 | Yes
F4 | Engagement, Training & Culture | Watch APF HR symposium recording (Golden Habits, TAPF Way) and share notes of what can be implemented. | Rajendra Prasad + Gnaneshwar | VERIFY | LOW | Group 10 & 12 Jul 2026 | RP: 'Ok'. Notes not seen. | Send notes (1 page). | 2026-11-10 | Yes
F5 | Engagement, Training & Culture | Collect participant feedback on 28-29 Jun sales training (Arjun's feedback shared); keep feedback window open. | Rajendra Prasad (HR Manager) | VERIFY | LOW | Group 29 Jun 2026 | Not seen. | Share feedback summary. | 2026-11-10
G2 | Policies & Documents | Mobile recharge policy (decent calling + data pack). | Rajendra Prasad (HR Manager) | VERIFY | LOW | Group 5 Oct 2025 | RP said he will create. Not seen. | Share policy. | 2026-11-10 | Yes
G3 | Policies & Documents | Map each telecaller to 1-2 preachers for knowledge transfer. | Rajendra Prasad (HR Manager) | VERIFY | LOW | Group 17 Sep 2025 | MKCD: 'Please do mapping immediately'. No mapping shared. | Share mapping sheet (may be superseded by Sai Vardhan structure). | 2026-11-10 | Yes
G6 | Policies & Documents | Certificate format for awards - finalise (printing for 1 year). | Rajendra Prasad (HR Manager) | VERIFY | LOW | Group 27 Feb - 2 Mar 2026 | MKCD: 'we'll finalise next week'. Not seen. | Confirm. | 2026-11-10
I17 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Verify and close stale HR tasks: Shashank termination notice (14yp17zmeny), TSF salary payments release (14yp17znrw1), PF withdrawal rules query from a kirtaniya (MASTER MA-00317), staff engagement planning review (MA-00919), volunteer details collection (MOM 86d3febpm). | Gnaneshwar (HR Executive) | VERIFY | LOW | ClickUp MKCP Assistant list; MOM lists; MASTER register | Status unknown; likely done or obsolete. | GN: confirm each and close in ClickUp with a one-line comment. | 2026-11-10 | Yes
I6 | I - Sweep: Claude Action Items / ClickUp / Notion / MASTER register | Collect dates of joining for all staff from Keka / GreytHR into the employee living documents (only 4 confirmed) and link every employee living doc from the Notion Leadership Hub and the HR roster sheet. | Gnaneshwar (HR Executive) | PENDING | LOW | Claude Action Items doc B8, D3 | Not started. | GN: export DOJ list from Keka; add to each doc; add links column in roster sheet. | 2026-11-10 | Yes

## Recurring Processes
ID | Category | Task / Instruction | Owner | Status | Priority | Source (chat & date) | Evidence / last update | Next action | Deadline | ClickUp task | Follow-up date | Latest remark (update here)
A6 | Performance & Daily Reporting | Monthly performance appraisal for every employee; salary paid in proportion to target achievement; compile monthly data for yearly appraisal (promotion / increment / termination). | Rajendra Prasad (HR Manager) | RECURRING | HIGH | Group 22 Mar, 3 May, 11 Oct 2026 | Policy stated repeatedly; telecaller proportional pay applied partly (Apr-May). Not yet systematic for all employees. Also ClickUp 14yp17zmem1 (performance-linked pay one-to-one). | Make it part of monthly payroll checklist from October 2026 payroll onwards. | Monthly / ongoing | Yes
A7 | Performance & Daily Reporting | Monthly late-login / LOP analysis report (Keka grace 10:05, 3 lates = half-day LOP). Exceptions only with MKCD email approval - same rule for all. | Gnaneshwar (HR Executive) | RECURRING | NORMAL | Group 12 May 2026 | April 2026 late-comers report delivered 12 May. MKCD: from today no exception without email approval. | Send every month with payroll; list any exception approvals attached. | Monthly / ongoing
C6 | Recruitment | Mandatory 4-round interview process (HR -> Shruthadev Prabhu -> Maha Bhuja Prabhu -> MKCD) + email per candidate with each round's feedback (subject: Position - Candidate - Date). Inform MKCD & STDD before any offer letter is issued. | Rajendra Prasad (HR Manager) | RECURRING | HIGH | Group 15 Oct 2025, 11 Jan, 14 Mar, 7 May 2026, 19-21 Oct 2026 | Lapses: Sumanth (SEO) hired without MKCD/STDD interview (May); 3-4 recent WFH appointments without informing STDD (19 Oct). RP agreed to fill gaps (21 Oct). | Written SOP circulated; no offer letter without MKCD/STDD sign-off email. | Monthly / ongoing | Yes
D7 | Onboarding, Trusts & Statutory | Employee Master Data + monthly & yearly CTC of ALL employees (on-roll and consultants) in a Google Sheet, updated on every joining / exit / revision; for budgeting. | Gnaneshwar (HR Executive) | RECURRING | HIGH | Group 16 May, 20 Aug, 25 Aug 2026; Gnaneshwar 1:1 7 Aug 2026 | CTC file delivered as Excel on 20 & 25 Aug. MKCD prefers Google Sheet links ('always send me in Google Sheet or email attachment'). | Keep one live Google Sheet; share link once; update within 1 day of any change. | Monthly / ongoing | Yes
E1 | Payroll & Finance | Pay sheets for all trusts to MKCD by 4th of every month (salary processed by 5th); include incentives & variable pay; share monthly attendance with each employee before payroll. | Rajendra Prasad + Gnaneshwar | RECURRING | HIGH | Group 2 Feb, 3 Mar, 4 Aug, 31 Aug, 5 Sep 2026; Rajendra 1:1 7 Feb 2026 | Generally met; occasional delays. October 2026 payroll to be performance-based (A3). | October payroll: attach performance % per employee. | Monthly / ongoing
E3 | Payroll & Finance | Same-day invoice to R Naveen (Finance) for every expense paid by card / UPI (Naukri, Apna, Lokal, Keka, etc.). | Rajendra Prasad + Gnaneshwar | RECURRING | NORMAL | Group 7 May, 8 Aug, 9 Sep 2026 | Apna invoice shared 9 Sep same day. Keep practice. | Standing rule. | Monthly / ongoing
F2 | Engagement, Training & Culture | Monthly team meeting + weekly snacks prasadam; gifts (smart watches, power banks) available with MKCD/MHBD. | Rajendra Prasad (HR Manager) | RECURRING | LOW | Group 17 Nov 2025, 12 May 2026 | Happening irregularly. | Fix calendar: 15th of every month. | Monthly / ongoing
F8 | Engagement, Training & Culture | Office discipline items raised by MHBD (AC/lights left on, late logins with remote punch, long breaks, no daily reports) - HR to take strict action and close; Gnaneshwar to check both floors before leaving. | Rajendra Prasad + Gnaneshwar | RECURRING | NORMAL | Group 3 Aug 2026 | 'Noted'. No closure report. | Closing checklist daily; monthly discipline summary. | Monthly / ongoing | Yes
G4 | Policies & Documents | Minutes of Meeting email after every management meeting (detailed, double-checked). | Rajendra Prasad (HR Manager) | RECURRING | LOW | Group 8 & 25 Oct 2025 | Expectation set; Otter summaries used since Sep 2026. | Standing rule. | Monthly / ongoing
G7 | Policies & Documents | Performance review / appraisal / increment cycle every March-April; HR team available in 1st week of every month (no leave). | Rajendra Prasad (HR Manager) | RECURRING | LOW | Group 3 Dec 2025, 2 Apr 2026 | Policy acknowledged. | Standing rule. | Monthly / ongoing

## R&R Additions
Role | Responsibility | Details / Standard | Frequency
Gnaneshwar - HR Executive (permanent / recurring responsibilities) | Daily Performance Report | Every working day by 11 AM: previous day's Target vs Actual for all 41 employees (drivers via register), red flags for non-achievers, late logins, unplanned leaves. Weekly, bi-weekly and monthly roll-ups. Shared as Google Sheet link + email to MKCD, STDD, RP. | Daily
Gnaneshwar - HR Executive (permanent / recurring responsibilities) | Daily Report compliance | Collect daily report emails with ClickUp / Tata Tele screenshots from every employee; mark LOP / 0.5-day penalty for misses after written warning; monthly non-compliance list with reasons and penalties. | Daily
Gnaneshwar - HR Executive (permanent / recurring responsibilities) | Daily attendance report | By 2 PM: present / absent / on-duty / week-off with Google Sheet link (already in practice - continue). | Daily
Gnaneshwar - HR Executive (permanent / recurring responsibilities) | ClickUp governance | Ensure every employee has a seat and logs 8.5 hours; coordinate with Hem Chand for users / training; weekly ClickUp + Tata Tele usage report. | Weekly
Gnaneshwar - HR Executive (permanent / recurring responsibilities) | Employee Master Data & CTC sheet | Single live Google Sheet: employee master (contacts, emergency contacts, address, documents link, trust, designation) and monthly / yearly CTC; update within 1 day of any join / exit / revision. | Monthly
Gnaneshwar - HR Executive (permanent / recurring responsibilities) | Attendance & late-login control | Monthly late-login / LOP analysis with payroll; exceptions only with MKCD email approval; biometric and remote-punch management; 1st-floor access list. | Monthly
Gnaneshwar - HR Executive (permanent / recurring responsibilities) | Appraisal data compilation | Chase and collect appraisal forms; compile monthly / half-yearly / annual performance data per employee for payroll and appraisal decisions. | Monthly
Gnaneshwar - HR Executive (permanent / recurring responsibilities) | Festival & event staffing | Participation sheets (Ratha Yatra, Janmashtami, Radhashtami), calling confirmations, same-day status updates, advance-funds and bills reconciliation with same-day invoices to Finance. | As required
Gnaneshwar - HR Executive (permanent / recurring responsibilities) | Recruitment support | Profile sourcing & screening, scheduling, Keka Hiring module data entry, candidate feedback emails in standard subject format. | As required
Gnaneshwar - HR Executive (permanent / recurring responsibilities) | Office closing & assets | Check both floors (lights, AC, fans) before leaving; ID cards; systems / equipment requirement list; TSF equipment returns. | Daily
Gnaneshwar - HR Executive (permanent / recurring responsibilities) | Weekly pending-task update | Every Monday: update the HR Task Tracker Google Sheet and email MKCD the pending list with status and support required. | Weekly
Gnaneshwar - HR Executive (permanent / recurring responsibilities) | Roster integrity & employee living documents | Every person paid on any trust appears in the HR roster with department, designation, date of joining, trust and a linked employee living document; reconcile roster vs pay sheets every month; link docs from the Notion Leadership Hub. | As required
Gnaneshwar - HR Executive (permanent / recurring responsibilities) | ClickUp hygiene across spaces | Weekly: close or merge duplicate / obsolete HR tasks in all ClickUp spaces (MKCP Assistant, Arjun Prabhu, MOM lists) and keep one live HR follow-up list. | Weekly
Rajendra Prasad - HR Manager (permanent / recurring responsibilities) | Performance Management System owner | Written targets for every employee (with reporting authorities); monthly appraisal; half-yearly and annual (March-April) cycle; salary proportional to performance; selection and rollout of an appraisal software. | Monthly
Rajendra Prasad - HR Manager (permanent / recurring responsibilities) | Recruitment pipeline owner | Tele Sales Manager, PPC expert, Digital Marketing Manager, CSR / BDE and other approved roles; mandatory 4-round process (HR -> STDD -> MHBD -> MKCD); inform MKCD & STDD before every offer letter; aptitude / psychometric tests; Keka Hiring module. | As required
Rajendra Prasad - HR Manager (permanent / recurring responsibilities) | Payroll & statutory | Pay sheets of all trusts to MKCD by 4th; incentives / variable pay included; monthly attendance to each employee before payroll; PF / ESI challans; salary advances and recoveries; consultant invoices. | Monthly
Rajendra Prasad - HR Manager (permanent / recurring responsibilities) | Trust structure & onboarding | Every employee / consultant on the correct trust as per MKCD's list; offer / appointment letters; RGI compliance; copies of letters to MKCD. | As required
Rajendra Prasad - HR Manager (permanent / recurring responsibilities) | Policies | Tour & Travel / Yatra allowance, mobile recharge, mobile-phone-at-work, Sunday & holiday annual roster, leave approvals, office hours, escalation discipline, non-performer exit with STDD. | As required
Rajendra Prasad - HR Manager (permanent / recurring responsibilities) | Rewards & Recognition | Extra Mile award on 15th of every month with data-backed review; quarterly awards; monthly team meeting with snacks prasadam. | Monthly
Rajendra Prasad - HR Manager (permanent / recurring responsibilities) | Training & development | Induction for new joiners; sales / team-building programs with recording, feedback and certificates; implement learnings from HR symposiums. | As required
Rajendra Prasad - HR Manager (permanent / recurring responsibilities) | Reporting to management | MoM after every management meeting; monthly HR dashboard (headcount, attrition, attendance, performance, recruitment status); weekly pending-task status with Gnaneshwar. | Weekly
Rajendra Prasad - HR Manager (permanent / recurring responsibilities) | Availability | HR Manager or HR Executive present in office during the 1st week of every month (payroll week); no simultaneous leave. | Monthly
Rajendra Prasad - HR Manager (permanent / recurring responsibilities) | Written warnings before payroll | Every non-performance / target-shortfall / unapproved-absence case gets a written warning email before the month's payroll, with the salary consequence stated; copies filed in the employee file and a list sent to MKCD. | Monthly
Rajendra Prasad - HR Manager (permanent / recurring responsibilities) | Exits, consultants & trust movements - due process | Performance record, notice, final settlement and letters for every exit; written consultancy agreements (scope, fee, IP, days on site); appointment letters and PF paperwork for every trust movement. | As required
Rajendra Prasad - HR Manager (permanent / recurring responsibilities) | Organisation structure & JD document owner | Maintain the department R&R documents and employee living documents: designation, JD, CTC and reporting line for every person (PID39-42); backup person and KT plan for every role (PID101); communicate structure changes to all staff. | As required
Rajendra Prasad - HR Manager (permanent / recurring responsibilities) | Policies & SOP library for HR | Recruitment & onboarding SOP, promotion policy, office-hours / Sunday / discipline circular, employee-monitoring disclosure; quarterly training calendar (PID15/16). | As required

## Change Log
Date | Updated by | Task ID | Change / remark
2026-10-25 | Claude (for MKCD) | ALL | Initial tracker built from WhatsApp exports (group chat Aug 2025 - Oct 2026, 1:1 chats with Rajendra Prasad and Gnaneshwar).