## Inputs
Bali Yatra 21-26 Jun 2027: inputs (yellow = edit; paste new quotes in column D, it overrides column B)
Item | Default | Unit | New quote (paste here) | Effective value | Source / status
IDR per Rs 1 (today) | 190.6446 | IDR |  | 190.6446 | XE mid-market, 23 Oct 2026
IDR per Rs 1 (previous basis) | 185 | IDR |  | 185 | Approx. Pluang, 22 Jul 2026 (184.8 to 185.8)
Paying yatris (planning size) | 35 | persons |  | 35 | Decision: 30 or more
Tour managers (our team) | 1 | persons |  | 1 | Assumption, confirm
Accompanying devotees (cost borne by us) | 2 | persons |  | 2 | Assumption, confirm (cook, kirtan lead, doctor etc.)
Target margin on selling price | 10% | % |  | 10% | ASSUMPTION: not given yet, replace
GST on package | 5% | % |  | 5% | 5% without ITC per secondary sources; CA to confirm
TCS on overseas tour package | 2% | % |  | 2% | 2% flat from 1 Apr 2026 (news/blogs); CA to confirm
Contingency on cost | 3% | % |  | 3% | Planning allowance, edit
Bank / payment charges on selling price | 1.5% | % |  | 1.5% | ASSUMPTION: confirm with bank
Seats per coach | 35 | seats |  | 35 | Operator quote: max 30-35 seater
Extra coach, cost per day | 1900000 | IDR |  | 1900000 | NOT VERIFIED: 27-seat 12h rate used as floor (mybalitrips.com)
Days an extra coach is needed | 4 | days |  | 4 | Itinerary: Days 2 to 5 (airport, Ubud, Kuta transfers)
Return flights HYD-KUL-DPS per person | 48000 | Rs |  | 48000 | PLACEHOLDER: Veena World Nov 2025 airfare ex-Bangalore; get HYD group quote
Land package per person, 4 nights twin | 35000 | Rs |  | 35000 | Veena World Nov 2025, 30+ pax, Option 1; get re-quote for Jun 2027
e-VOA visa fee per person | 750000 | IDR |  | 750000 | Announced rise 12 Aug 2026 (The Star); official page still shows 500,000. Effective date NOT VERIFIED
e-VOA fee, previous basis | 500000 | IDR |  | 500000 | Official e-VOA page, 23 Oct 2026
Bali tourist levy per person | 150000 | IDR |  | 150000 | lovebali.baliprov.go.id
Yatri kit (bag, cap, ID card, handbook) | 0 | Rs |  | 0 | TBC: no quote yet
Senior insurance top-up (age 60+), average per yatri | 0 | Rs |  | 0 | TBC: get group quote with age bands
Satvik arrangements beyond package (boxed lunch, snacks) | 0 | Rs |  | 0 | TBC: no quote yet
Hyderabad local transfers per yatri | 0 | Rs |  | 0 | TBC: no quote yet
Proposed selling price per yatri, before GST (optional) |  | Rs |  | 0 | Enter to see the margin it gives

## Itinerary
Day-by-day itinerary (tentative: flights and ashram timings not confirmed; km are approximate, check each link before fixing)
Day | Date | Start | End | Clock shift (h) | Duration (h) | Duration | Activity | Place | Google Maps | Transport | Approx km | What we do | Meal / who provides
1 | 2027-06-21 | 46559.7292 | 46559.7812 | 0 | 1.25 | 1h 15m | Satvik dinner and pre-departure briefing | Hare Krishna Golden Temple, Hyderabad | Open map | On foot | 0 | Prasadam, briefing on documents, dress, health, group rules. Garland the Deities, offer prayers for a safe yatra. | Dinner: HKGT prasadam (confirm)
1 | 2027-06-21 | 46559.7812 | 46559.8333 | 0 | 1.25 | 1h 15m | Coach to airport | Rajiv Gandhi International Airport, Hyderabad | Open map | Coach | 30 | Allow 1h15m for evening traffic. | -
1 | 2027-06-21 | 46559.8333 | 46559.9965 | 0 | 3.92 | 3h 55m | Group check-in, emigration, boarding | Rajiv Gandhi International Airport, Hyderabad | Open map | Walk | 0 | Report 3h 55m before departure; seniors get wheelchair help on request. | Own snacks (Satvik kit)
1 | 2027-06-21 | 46559.9965 | 46560.2917 | 2.5 | 4.58 | 4h 35m | Flight HYD to Kuala Lumpur (AirAsia AK068, TENTATIVE) | Kuala Lumpur International Airport | Open map | Flight | 0 | Schedule from Oct 2026 snapshot; June 2027 not open. Operates Mon/Tue/Wed/Sat in that pattern. | On board: own prasadam snacks
2 | 2027-06-22 | 46560.2917 | 46560.375 | 0 | 2 | 2h 00m | Transit at Kuala Lumpur | Kuala Lumpur International Airport | Open map | Walk | 0 | Immigration and transit; Satvik breakfast kit from Hyderabad. | Breakfast: carried Satvik kit
2 | 2027-06-22 | 46560.375 | 46560.5104 | 0 | 3.25 | 3h 15m | Flight KUL to Bali (AirAsia AK364, TENTATIVE) | Ngurah Rai International Airport, Bali | Open map | Flight | 0 | KUL and Bali share the same time zone (UTC+8). | On board: own snacks
2 | 2027-06-22 | 46560.5104 | 46560.5833 | 0 | 1.75 | 1h 45m | Arrival: immigration (e-VOA), bags, meet guide | Ngurah Rai International Airport, Bali | Open map | Walk | 0 | Pre-paid e-VOA and arrival card QR codes ready. Levy vouchers. Allow 1h 45m for 35 persons. | -
2 | 2027-06-22 | 46560.5833 | 46560.5972 | 0 | 0.33 | 0h 20m | Coach to lunch | Vrindavan Pure Veg Restaurant, Kuta | Open map | Coach | 5 | Short hop from the airport. | -
2 | 2027-06-22 | 46560.5972 | 46560.6458 | 0 | 1.17 | 1h 10m | Lunch | Vrindavan Pure Veg Restaurant, Kuta | Open map | On foot | 0 | Confirm group size, no onion-garlic cooking and booking in writing. Fallback: pre-ordered boxed lunch. | Lunch: Indian pure-veg restaurant (to book)
2 | 2027-06-22 | 46560.6458 | 46560.6979 | 0 | 1.25 | 1h 15m | Coach to ISKCON Bali | Sri Sri Radha Madhava Mandir, Bitera, Gianyar | Open map | Coach | 35 | Address from a 2011 article: confirm location and timings with the temple. | -
2 | 2027-06-22 | 46560.6979 | 46560.7917 | 0 | 2.25 | 2h 15m | Darshan, kirtan and prasadam at ISKCON Bali (TIMINGS TBC) | Sri Sri Radha Madhava Mandir, Bitera, Gianyar | Open map | On foot | 0 | Temple darshan and sandhya arati if timed; group prasadam dinner only if the temple agrees (not verified). | Dinner: ISKCON Bali prasadam (to request)
2 | 2027-06-22 | 46560.7917 | 46560.8229 | 0 | 0.75 | 0h 45m | Coach to Ubud hotel | Ubud hotel (hotel TBC) | Open map | Coach | 15 | Distance is approximate. | -
2 | 2027-06-22 | 46560.8229 | 46560.8542 | 0 | 0.75 | 0h 45m | Hotel check-in and rest | Ubud hotel (hotel TBC) | Open map | - | 0 | Rooms list ready; early rest after the long journey. Overnight Ubud. | Dinner fallback: hotel Satvik meal
3 | 2027-06-23 | 46561.2917 | 46561.3438 | 0 | 1.25 | 1h 15m | Breakfast | Ubud hotel (hotel TBC) | Open map | - | 0 | Satvik breakfast arranged with the hotel in advance. | Breakfast: hotel
3 | 2027-06-23 | 46561.3438 | 46561.375 | 0 | 0.75 | 0h 45m | Coach to Tirta Empul | Tirta Empul Temple, Tampaksiring | Open map | Coach | 15 | Temple opens 09:00. | -
3 | 2027-06-23 | 46561.375 | 46561.4583 | 0 | 2 | 2h 00m | Tirta Empul holy spring temple | Tirta Empul Temple, Tampaksiring | Open map | On foot | 0 | Optional ritual bath (sarong and sash, spare dry clothes). Women: Bali temple rule on menstruation applies. Steps are wet: stay with the group. | -
3 | 2027-06-23 | 46561.4583 | 46561.4896 | 0 | 0.75 | 0h 45m | Coach to Ubud | Ubud centre | Open map | Coach | 15 | - | -
3 | 2027-06-23 | 46561.4896 | 46561.5417 | 0 | 1.25 | 1h 15m | Lunch | Madhubann Pure Veg Indian, Ubud | Open map | On foot | 0 | Pure veg, Jain thali reported. Confirm group booking and no onion-garlic. | Lunch: Indian pure-veg restaurant (to book)
3 | 2027-06-23 | 46561.5417 | 46561.6042 | 0 | 1.5 | 1h 30m | Sacred Monkey Forest | Sacred Monkey Forest Sanctuary, Ubud | Open map | Coach / walk | 2 | Slow 1h walk on shaded paths. Hold glasses, phones and food: monkeys snatch. Hours 09:00 to 18:00. | -
3 | 2027-06-23 | 46561.6042 | 46561.6667 | 0 | 1.5 | 1h 30m | Rest at hotel | Ubud hotel (hotel TBC) | Open map | Rest (short coach hop) | 3 | Seniors rest in the heat of the day. | Tea / snack: hotel
3 | 2027-06-23 | 46561.6667 | 46561.7292 | 0 | 1.5 | 1h 30m | Taman Saraswati and Ubud village walk (optional shopping) | Pura Taman Saraswati, Ubud | Open map | Coach / walk | 3 | Lotus pond temple, short flat walk; local shopping. | -
3 | 2027-06-23 | 46561.75 | 46561.7917 | 0 | 1 | 1h 00m | Sandhya kirtan and talk | Ubud hotel (hotel TBC) | Open map | - | 0 | Hall to be arranged. | -
3 | 2027-06-23 | 46561.7917 | 46561.8438 | 0 | 1.25 | 1h 15m | Dinner | Ubud hotel (hotel TBC) | Open map | - | 0 | Satvik dinner arranged with the hotel. | Dinner: hotel
4 | 2027-06-24 | 46562.2917 | 46562.3542 | 0 | 1.5 | 1h 30m | Breakfast and check-out | Ubud hotel (hotel TBC) | Open map | - | 0 | Luggage loaded by 08:15. | Breakfast: hotel (and boxed lunch pick-up)
4 | 2027-06-24 | 46562.3542 | 46562.4271 | 0 | 1.75 | 1h 45m | Coach to Bedugul | Pura Ulun Danu Beratan, Bedugul | Open map | Coach | 50 | Winding mountain road: seat seniors at the front, motion-sickness tablets. | -
4 | 2027-06-24 | 46562.4271 | 46562.4896 | 0 | 1.5 | 1h 30m | Ulun Danu Beratan temple on Lake Beratan | Pura Ulun Danu Beratan, Bedugul | Open map | On foot | 0 | Cool and misty at about 1,200 m. Flat gardens, easy for seniors. Carry a light jacket. | -
4 | 2027-06-24 | 46562.4896 | 46562.5312 | 0 | 1 | 1h 00m | Boxed Satvik lunch in the garden | Pura Ulun Danu Beratan, Bedugul | Open map | On foot | 0 | No verified restaurant at Bedugul: pre-order boxed lunches from a vegetarian restaurant. | Lunch: pre-ordered boxes (to book)
4 | 2027-06-24 | 46562.5312 | 46562.6146 | 0 | 2 | 2h 00m | Coach to Kuta hotel | Kuta hotel (hotel TBC) | Open map | Coach | 60 | Check-in: early check-in subject to availability; leave luggage if rooms are not ready. | -
4 | 2027-06-24 | 46562.6146 | 46562.6771 | 0 | 1.5 | 1h 30m | Hotel check-in and rest | Kuta hotel (hotel TBC) | Open map | - | 0 | Rest before Tanah Lot. | Tea: hotel
4 | 2027-06-24 | 46562.6771 | 46562.7188 | 0 | 1 | 1h 00m | Coach to Tanah Lot | Tanah Lot Temple, Tabanan | Open map | Coach | 20 | Evening traffic: leave on time. | -
4 | 2027-06-24 | 46562.7188 | 46562.7812 | 0 | 1.5 | 1h 30m | Tanah Lot sea temple and sunset (sunset about 18:10) | Tanah Lot Temple, Tabanan | Open map | On foot | 0 | Steps are uneven and crowded; seniors may view from the upper cliff path. Shopping on the way. | -
4 | 2027-06-24 | 46562.7812 | 46562.8229 | 0 | 1 | 1h 00m | Coach to Kuta hotel | Kuta hotel (hotel TBC) | Open map | Coach | 20 | - | -
4 | 2027-06-24 | 46562.8229 | 46562.875 | 0 | 1.25 | 1h 15m | Dinner | Kuta hotel (hotel TBC) | Open map | - | 0 | Satvik dinner with the hotel or Shiv Sagar, Seminyak (pure veg). | Dinner: hotel / pure-veg restaurant
5 | 2027-06-25 | 46563.3021 | 46563.3542 | 0 | 1.25 | 1h 15m | Breakfast | Kuta hotel (hotel TBC) | Open map | - | 0 | - | Breakfast: hotel
5 | 2027-06-25 | 46563.3542 | 46563.3889 | 0 | 0.83 | 0h 50m | Coach to GWK | Garuda Wisnu Kencana Cultural Park, Ungasan | Open map | Coach | 22 | - | -
5 | 2027-06-25 | 46563.3889 | 46563.4931 | 0 | 2.5 | 2h 30m | Garuda Wisnu Kencana Cultural Park | Garuda Wisnu Kencana Cultural Park, Ungasan | Open map | On foot | 0 | Giant Lord Vishnu on Garuda statue and plazas. Opening hours conflict in sources: confirm. Buggy help for seniors if offered. | -
5 | 2027-06-25 | 46563.4931 | 46563.5243 | 0 | 0.75 | 0h 45m | Coach to lunch | Vinayak Pure Veg, Lippo Mall Kuta | Open map | Coach | 22 | - | -
5 | 2027-06-25 | 46563.5243 | 46563.5833 | 0 | 1.42 | 1h 25m | Lunch | Vinayak Pure Veg, Lippo Mall Kuta | Open map | On foot | 0 | Pure veg with Jain-style cooking reported; confirm group booking. | Lunch: Indian pure-veg restaurant (to book)
5 | 2027-06-25 | 46563.5833 | 46563.6458 | 0 | 1.5 | 1h 30m | Rest at hotel | Kuta hotel (hotel TBC) | Open map | Rest (short coach hop) | 5 | - | -
5 | 2027-06-25 | 46563.6458 | 46563.6875 | 0 | 1 | 1h 00m | Coach to Uluwatu | Uluwatu Temple, Pecatu | Open map | Coach | 25 | - | -
5 | 2027-06-25 | 46563.6875 | 46563.75 | 0 | 1.5 | 1h 30m | Uluwatu cliff temple (sunset about 18:10) | Uluwatu Temple, Pecatu | Open map | On foot | 0 | Monkeys steal glasses and phones. Steps along the cliff: optional shorter walk for seniors. | -
5 | 2027-06-25 | 46563.75 | 46563.7917 | 0 | 1 | 1h 00m | Kecak fire dance (OPTIONAL, separate ticket) | Uluwatu Temple amphitheatre, Pecatu | Open map | On foot | 0 | Shows 18:00 and 19:00; those not joining wait in the coach or cafe. | -
5 | 2027-06-25 | 46563.7917 | 46563.8333 | 0 | 1 | 1h 00m | Coach to Kuta hotel | Kuta hotel (hotel TBC) | Open map | Coach | 25 | - | -
5 | 2027-06-25 | 46563.8333 | 46563.8854 | 0 | 1.25 | 1h 15m | Dinner | Kuta hotel (hotel TBC) | Open map | - | 0 | Satvik dinner at the hotel. | Dinner: hotel
6 | 2027-06-26 | 46564.2917 | 46564.3542 | 0 | 1.5 | 1h 30m | Breakfast | Kuta hotel (hotel TBC) | Open map | - | 0 | - | Breakfast: hotel
6 | 2027-06-26 | 46564.3646 | 46564.3854 | 0 | 0.5 | 0h 30m | Coach to Krishna Oleh-Oleh | Krishna Oleh-Oleh, Bali (branch TBC) | Open map | Coach | 6 | Souvenirs and snacks (check Satvik labels). | -
6 | 2027-06-26 | 46564.3854 | 46564.4583 | 0 | 1.75 | 1h 45m | Shopping and free time | Krishna Oleh-Oleh, Bali (branch TBC) | Open map | On foot | 0 | Group photo; keep an eye on the time. | -
6 | 2027-06-26 | 46564.4583 | 46564.4792 | 0 | 0.5 | 0h 30m | Coach to lunch and check-out | Vrindavan Pure Veg Restaurant, Kuta | Open map | Coach | 6 | Luggage loaded after check-out (hotel check-out time TBC). | -
6 | 2027-06-26 | 46564.4792 | 46564.5417 | 0 | 1.5 | 1h 30m | Lunch | Vrindavan Pure Veg Restaurant, Kuta | Open map | On foot | 0 | - | Lunch: Indian pure-veg restaurant (to book)
6 | 2027-06-26 | 46564.5417 | 46564.5625 | 0 | 0.5 | 0h 30m | Coach to airport | Ngurah Rai International Airport, Bali | Open map | Coach | 5 | - | -
6 | 2027-06-26 | 46564.5625 | 46564.684 | 0 | 2.92 | 2h 55m | Check-in, immigration, boarding | Ngurah Rai International Airport, Bali | Open map | Walk | 0 | Flight times TBC. | -
6 | 2027-06-26 | 46564.684 | 46564.816 | 0 | 3.17 | 3h 10m | Flight Bali to Kuala Lumpur (ASSUMED, Malaysia Airlines pattern) | Kuala Lumpur International Airport | Open map | Flight | 0 | NOT VERIFIED: no Bali to Hyderabad schedule found. | On board: own snacks
6 | 2027-06-26 | 46564.816 | 46564.8924 | 0 | 1.83 | 1h 50m | Transit at Kuala Lumpur | Kuala Lumpur International Airport | Open map | Walk | 0 | Transit, dinner from carried Satvik kit. | Dinner: carried Satvik kit
6 | 2027-06-26 | 46564.8924 | 46564.9722 | -2.5 | 4.42 | 4h 25m | Flight KUL to Hyderabad (ASSUMED: MH198 pattern) | Rajiv Gandhi International Airport, Hyderabad | Open map | Flight | 0 | Arrival time is India time (IST). NOT VERIFIED for 2027. | On board: own snacks

## Day summary
Day summary (formulas read the Itinerary sheet)
Day | Date | Route | Overnight | Approx km | Coach hours | Flight hours (clock-adjusted) | Driver check (8h baseline) | Sunrise | Sunset
1 | 2027-06-21 | Hyderabad to airport, overnight flight via Kuala Lumpur | In flight | 30 | 1.25 | 4.58 | OK | n/a (Hyderabad) | n/a
2 | 2027-06-22 | Kuala Lumpur, Bali airport, Kuta lunch, ISKCON Bitera, Ubud | Ubud | 55 | 2.33 | 3.25 | OK | 06:32 | 18:09
3 | 2027-06-23 | Tirta Empul, Ubud, Monkey Forest, Saraswati | Ubud | 38 | 1.5 | 0 | OK | 06:32 | 18:09
4 | 2027-06-24 | Ubud to Bedugul to Kuta, Tanah Lot | Kuta | 150 | 5.75 | 0 | OK | 06:32 | 18:10
5 | 2027-06-25 | GWK, Kuta, Uluwatu | Kuta | 99 | 3.58 | 0 | OK | 06:33 | 18:10
6 | 2027-06-26 | Krishna Oleh-Oleh, airport, flights home | In flight / Hyderabad (late night) | 17 | 1.5 | 7.59 | OK | 06:33 | 18:10
Total |  |  |  | 389 | 15.91 | 15.42
Sunrise and sunset: Denpasar, sunrise-sunset.org, checked 23 Oct 2026. Driver-hour baseline: Indonesian Law 22/2009 Art. 90 (8h/day, 30 min rest after 4h); local confirmation pending.
Coach hours count driving legs only; short hops to and from hotel rests (about 20 min) are not counted.

## Meal plan
Meal plan (Satvik only: no onion, garlic, eggs, meat, fish). No Ekadasi on 21-26 Jun 2027 (Nirjala 14/15 Jun; Yogini 30 Jun).
Day | Date | Breakfast | Lunch | Dinner | Notes
1 | 2027-06-21 | Home | Home | HKGT prasadam before departure (confirm); Satvik snack kit on the flight | Pack Satvik kit for the long journey
2 | 2027-06-22 | Carried Satvik kit at KUL | Vrindavan Pure Veg, Kuta (to book) | ISKCON Bali prasadam (to request); fallback hotel | Written Satvik confirmation needed from every provider
3 | 2027-06-23 | Ubud hotel | Madhubann Pure Veg Indian, Ubud (to book) | Ubud hotel | Hotel kitchen must cook without onion/garlic
4 | 2027-06-24 | Ubud hotel | Boxed Satvik lunch at Bedugul (to book) | Kuta hotel or Shiv Sagar, Seminyak (to book) | No verified restaurant near Bedugul
5 | 2027-06-25 | Kuta hotel | Vinayak, Lippo Mall Kuta (to book) | Kuta hotel | Kecak evening is optional; dinner may be late
6 | 2027-06-26 | Kuta hotel | Vrindavan Pure Veg, Kuta (to book) | Carried Satvik kit at KUL | Hyderabad arrival about 23:20

## Tickets
Entry tickets, adult rate (not official except Monkey Forest; no senior or group concession found). IDR converted at Inputs rate.
Site | Status | Adult IDR | Adult Rs | Qty (yatris) | Total IDR | Total Rs | Source / note
Sacred Monkey Forest, Ubud | Planned | 130000 | 682 | 35 | 4550000 | 23866 | Official site
Tirta Empul | Planned | 75000 | 393 | 35 | 2625000 | 13769 | Guide, baliholidaysecrets.com; others say 50,000
Pura Ulun Danu Beratan | Planned | 100000 | 525 | 35 | 3500000 | 18359 | Same guide; others 50,000 to 75,000
Taman Saraswati, Ubud | Planned | 60000 | 315 | 35 | 2100000 | 11015 | Guide conflict (free to 60,000): upper used
Tanah Lot | Planned | 75000 | 393 | 35 | 2625000 | 13769 | Same guide
GWK Cultural Park | Planned | 150000 | 787 | 35 | 5250000 | 27538 | Same guide; official site shows price only after date selection
Uluwatu Temple | Planned | 60000 | 315 | 35 | 2100000 | 11015 | Same guide; another says 50,000
Kecak fire dance, Uluwatu | Optional | 150000 | 787 | 35 | 5250000 | 27538 | Same guide; 100,000 to 200,000 elsewhere
Goa Gajah | Optional | 50000 | 262 | 35 | 1750000 | 9179 | Not in route; kept as option
Tegallalang rice terrace | Optional | 50000 | 262 | 35 | 1750000 | 9179 | Not recommended for seniors
Ubud Palace | Optional | 0 | 0 | 35 | 0 | 0 | Free per guide
ISKCON Bali ashram | Planned | 0 | 0 | 35 | 0 | 0 | Voluntary donation
Planned total per adult |  | 650000 | 3409 |  | 22750000 | 119332
Optional total per adult (if all taken) |  | 250000 | 1311
Tickets are assumed to be inside the operator land package (the quote says both yes and no). If not, add the planned total to the budget as a cost.

## Budget
Budget per yatri at the planning size (Inputs!B6). Previous basis = old FX and old visa fee; Current = today's rate and latest quotes.
Line | Previous basis Rs | Current Rs | Change Rs | Change % | Status
Return flights HYD-KUL-DPS | 48000 | 48000 | 0 | 0% | PLACEHOLDER: old ex-Bangalore airfare
Land package, 4 nights twin (hotels, meals, coach, guide, tips, tickets) | 35000 | 35000 | 0 | 0% | Quote Nov 2025 for Apr 2026: re-quote needed
Extra coach share (only above seat capacity) | 0 | 0 | 0 | 0% | NOT VERIFIED coach rate
e-VOA visa fee | 2702.7027 | 3934.0217 | 1231.319 | 45.56% | Fee rise announced, effective date NOT VERIFIED
Bali tourist levy | 810.8108 | 786.8043 | -24.0065 | -2.961% | Official portal
Yatri kit | 0 | 0 | 0 | 0% | TBC
Senior insurance top-up | 0 | 0 | 0 | 0% | TBC
Satvik arrangements beyond package | 0 | 0 | 0 | 0% | TBC
Hyderabad local transfers | 0 | 0 | 0 | 0% | TBC
Tour manager and accompanying devotees (cost shared by paying yatris) | 7415.444 | 7518.9279 | 103.4839 | 1.396% | Assumption: 1 + 2 persons
Sub-total | 93928.9575 | 95239.754 | 1310.7965 | 1.396%
Contingency | 2817.8687 | 2857.1926 | 39.3239 | 1.396%
COST PER YATRI | 96746.8263 | 98096.9467 | 1350.1204 | 1.396%
Price before GST for the target margin (bank charges included) | 109318.4477 | 110844.0075 | 1525.5598 | 1.396%
GST | 5465.9224 | 5542.2004 | 76.278 | 1.396%
Price including GST | 114784.3701 | 116386.2079 | 1601.8378 | 1.396%
TCS (collected from the yatri, adjustable against their income tax) | 2295.6874 | 2327.7242 | 32.0368 | 1.396%
TOTAL PAYABLE BY YATRI | 117080.0575 | 118713.9321 | 1633.8745 | 1.396%
Margin at your proposed selling price (Inputs: selling price before GST) |  | enter a price in Inputs
Gap: price needed minus proposed selling price

## Sensitivity
Cost per yatri and price needed, by group size (current basis)
Yatris | Extra coaches | Flights | Land package | Extra coach share | e-VOA | Levy | Other (kit, insurance, Satvik, transfers) | Team share (TM + devotees) | Contingency | COST per yatri | Price before GST at target margin | Incl. 5% GST | Incl. TCS (total payable) | Price at 5% margin | Price at 10% margin | Price at 15% margin | Price at 20% margin
30 | 0 | 48000 | 35000 | 0 | 3934.0217 | 786.8043 | 0 | 8772.0826 | 2894.7873 | 99387.696 | 112302.4813 | 117917.6054 | 120275.9575 | 106297.001 | 112302.4813 | 119027.1808 | 126608.5299
35 | 0 | 48000 | 35000 | 0 | 3934.0217 | 786.8043 | 0 | 7518.9279 | 2857.1926 | 98096.9467 | 110844.0075 | 116386.2079 | 118713.9321 | 104916.5205 | 110844.0075 | 117481.3732 | 124964.2633
40 | 1 | 48000 | 35000 | 996.6188 | 3934.0217 | 786.8043 | 0 | 6579.062 | 2858.8952 | 98155.4021 | 110910.0589 | 116455.5618 | 118784.673 | 104979.0397 | 110910.0589 | 117551.3797 | 125038.7288
45 | 1 | 48000 | 35000 | 885.8834 | 3934.0217 | 786.8043 | 0 | 5848.0551 | 2833.6429 | 97288.4075 | 109930.404 | 115426.9242 | 117735.4626 | 104051.7727 | 109930.404 | 116513.0629 | 123934.2771
49 | 1 | 48000 | 35000 | 813.5664 | 3934.0217 | 786.8043 | 0 | 5370.6628 | 2817.1517 | 96722.207 | 109290.6293 | 114755.1608 | 117050.264 | 103446.2107 | 109290.6293 | 115834.9784 | 123213.0025
Note: the operator land slab is flat for 30 or more guests, so the cost per yatri changes with group size only through the extra coach, the shared team cost and rounding.

## Open points
# | Open point to verify | Owner
1 | Flights HYD-DPS-HYD for Jun 2027: get written group quotes (MH, AirAsia/Batik). Monday 21 Jun arrival needs a Sunday-night departure, which the current AirAsia pattern does not operate. | TBC
2 | Return DPS to HYD times and airline: not found. | TBC
3 | e-VOA fee: IDR 500,000 (official page) or IDR 750,000 (announced rise, 12 Aug 2026)? Effective date. | TBC
4 | Hotel names, star ratings, Jun 2027 twin rate and ++ taxes (10%/11% tax, 10% service). | TBC
5 | Land package re-quote for Jun 2027 (4 nights), with written Satvik confirmation and whether entry tickets are included. | TBC
6 | ISKCON Bali Bitera: current address, programme times, group prasadam, contact. | TBC
7 | Restaurants: group capacity, price and no onion-garlic for Vrindavan, Madhubann, Vinayak, Shiv Sagar; boxed lunch for Bedugul. | TBC
8 | Entry ticket prices from official sources; senior or group concessions. | TBC
9 | Bali Arts Festival 2027 dates (likely overlap, Denpasar road closures). | TBC
10 | Menstruation rule at temples: brief women yatris; confirm site policies. | TBC
11 | Senior insurance (60+) group quote; medical fitness forms. | TBC
12 | TCS 2% and GST 5% treatment: CA confirmation. | TBC
13 | Organiser names, phone numbers, website, handles for the brand block. | TBC
14 | Target margin and selling price. | TBC
15 | Yatra team: number of tour managers and accompanying devotees. | TBC