Hare Krishna

Prasadam, Sweets & Savories Vertical

Project Management Plan

Hare Krishna Golden Temple (ISKCON), Banjara Hills, Hyderabad

Prepared for: Temple management, Production (Prabhu) and DMTT

Source: Prasadam Revenue Generation Plan meeting, 26 September 2026

v1.2, 21 October 2026

Figures marked [ESTIMATE] are planning assumptions. Replace them with the 6–12 month order data before committing budget.

# Contents

1. Project charter

2. Objectives and success criteria

3. Scope

4. Stakeholders

5. Organisation and RACI

6. Work breakdown structure and schedule

7. Milestones

8. Budget

9. Risk register

10. Quality management

11. Communication plan

12. Governance and reporting

13. Change control

14. Issue and decision log

15. Action items

# 1. Project charter

| Field | Detail |
| --- | --- |
| Project name | Prasadam, Sweets & Savories Vertical launch |
| Organisation | Hare Krishna Golden Temple (ISKCON), Banjara Hills, Hyderabad |
| Sponsor | Temple leadership |
| Project lead | Mukunda Dasa (marketing, sales, technology) |
| Production lead | Prabhu (temple production) |
| Start / pilot end / Year-1 end | 26 Sep 2026 / 30 Nov 2026 / 30 Sep 2027 |
| Purpose | Offer pure, satvik, preservative-free prasadam, prepared with devotion and offered to Sri Sri Radha Krishna, to every audience we already touch: visitors, donors, devotees, companies, institutions, communities and online buyers. Production is done by the temple kitchen; marketing, technology and sales are done by the DMTT; every rupee and hour is tracked for ROI. |
| Business case | Proven festival demand, strong brand, warm B2B network and existing systems; two-tier pricing makes the kitchen viable; Year-1 revenue about ₹2.2 crore [ESTIMATE]. |
| Key constraints | Kitchen capacity (4 staff), no historic cost data compiled, festival deadlines fixed, brand-use approval needed. |
| Assumptions | Departments move all prasadam orders in-house; B2B orders take 50% advance; seasonal staff available at short notice. |

# 2. Objectives and success criteria

| # | Objective | Success criterion |
| --- | --- | --- |
| O1 | Launch the vertical with a ready sales kit | Catalogue, prices, samples and packaging ready by 10 Oct 2026 |
| O2 | Win Dasara/Diwali corporate orders | ≥ 5,000 gift boxes and ≥ 10 corporate/institution clients by 8 Nov 2026 [ESTIMATE] |
| O3 | Stabilise internal supply | 100% of internal prasadam orders placed with in-house production by Nov 2026 |
| O4 | Go online | Shopify + Amazon live with ≥ 12 SKUs by 31 Jan 2027 |
| O5 | 10× festival counters | Janmashtami 2027 counter sales ≥ ₹60 lakh (10× 2026) as stretch; ₹30 lakh base |
| O6 | Prove ROI | Monthly DMTT ROI report from Nov 2026; vertical cash-positive by month 6 |
| O7 | Year-1 revenue | ₹2.2 crore gross revenue Oct 2026–Sep 2027 [ESTIMATE] |

# 3. Scope

## In scope

Sweets, savories, gift boxes, pickles/papads/powders

Internal supply, festival stalls, restaurant/lawn, corporate & white-label gifting

E-commerce, gated communities, outbound B2B, catering (pilot scale), donor packs

Packaging, pricing, marketing, technology, ROI tracking

Planning for QSR partnership and exports (execution later phases)

## Out of scope (Year 1)

Building a new dedicated production facility in Year 1

Opening QSR outlets in Year 1

Education company, games, audio/video, advertising projects (separate initiatives)

Dairy/ghee production (evaluate separately)

## Deliverables

Approved business plan and charter

Demand forecast from 6–12 months of order data

Product list, recipes, costing, price list

Sales kit: catalogue, menu, sample boxes, white-label templates

Festival stall SOP and layout

Internal weekly order system

Shopify store and Amazon listing

ROI dashboard (monthly)

Pilot review report

Year-1 review and Year-2 budget

# 4. Stakeholders

| Stakeholder | Interest | Influence | Engagement |
| --- | --- | --- | --- |
| Temple leadership | Revenue, reputation, sanctity of prasadam | High | Quarterly steering, monthly ROI |
| Production lead & kitchen team | Workable volumes, fair staffing | High | Weekly plan, daily in festival weeks |
| Production manager | Resource commitments | High | Decision meeting, monthly review |
| DMTT | Marketing, tech, data, ROI | High | Weekly |
| Internal departments | Reliable supply, price | Medium | Order cut-offs, monthly budget |
| Corporate clients & institutions | Quality, on-time, branding | Medium | Account management |
| Donors & devotees | Purity, devotion, value | Medium | Campaigns |
| QSR partner | Brand licence, scale | Medium | Year-2 negotiations |
| Regulators (FSSAI, GST) | Compliance | High | Licences, audits |

# 5. Organisation and RACI

| Role | Person | Responsibility |
| --- | --- | --- |
| Executive sponsor | Temple leadership | Approves budget, brand use and major decisions |
| Vertical lead – marketing, sales & technology | Mukunda Dasa | Vision, network, marketing, e-commerce, DMTT reporting |
| Production lead | Prabhu (production) | Recipes, costing, samples, capacity, kitchen team |
| Production manager (reporting line) | Production lead's manager | Approves production commitments and resources |
| E-commerce & logistics advisor | Subhadra Radha Devi Mataji | Shopify/Amazon, fastest shipping |
| Corporate sales representative | To be assigned by Mukunda Dasa | Joins owner meetings; manages B2B pipeline |
| Order coordinator (new hire) | To hire now | Order confirmations, internal orders, production calendar |
| Design & packaging | DMTT designer | Catalogue, boxes, stickers, white-label mock-ups |
| Data & AI | DMTT data scientists | Demand analysis, targeting, ROI dashboard |
| Finance | Accounts team | Cost centre, GST, P&L, ROI |
| Quality & compliance | To assign | FSSAI, labelling, hygiene audits |

## RACI matrix

R = Responsible, A = Accountable, C = Consulted, I = Informed.

| Activity | Sponsor | Mukunda Dasa | Production lead | Prod. manager | DMTT | Sales rep | Finance | Quality |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vertical strategy & budget | A | R | C | C | C | I | C | I |
| Product list, recipes, samples | I | C | R/A | C | I | I | I | C |
| Costing & pricing | I | A | R | C | C | C | C | I |
| Packaging & catalogue design | I | A | C | I | R | C | I | C |
| Corporate & white-label sales | I | A | C | I | C | R | I | I |
| Festival stalls | I | A | R | C | C | C | C | C |
| Internal weekly orders | I | A | R | I | C | I | C | I |
| E-commerce & logistics | I | A | C | I | R | I | C | I |
| Compliance (FSSAI, labels, hygiene) | I | C | R | C | I | I | I | A |
| ROI tracking & reporting | I | A | C | I | R | I | R | I |
| Hiring & staffing | I | C | R | A | I | I | C | I |
| Capex (pagodas, machines, unit) | A | R | C | C | I | I | C | C |

# 6. Work breakdown structure and schedule

The same WBS, with a Gantt view, is in 05_Project_Tracker.xlsx for day-to-day updates.

| ID | Task | Owner | Start | End | Depends |
| --- | --- | --- | --- | --- | --- |
| 1 | Initiation & governance |  | 26 Sep 26 | 10 Oct 26 |  |
| 1.1 | Send detailed vertical plan to stakeholders | Mukunda Dasa | 26 Sep 26 | 30 Sep 26 |  |
| 1.2 | Production lead reviews plan with his manager | Production lead | 30 Sep 26 | 03 Oct 26 | 1.1 |
| 1.3 | Decision meeting (Mukunda Dasa, production lead, manager) | Mukunda Dasa | 05 Oct 26 | 05 Oct 26 | 1.2 |
| 1.4 | Set up DMTT cost centre and ROI tracker | DMTT / Finance | 29 Sep 26 | 06 Oct 26 |  |
| 1.5 | Confirm brand-use approval and FSSAI scope | Quality & compliance | 29 Sep 26 | 09 Oct 26 |  |
| 2 | Demand & data |  | 26 Sep 26 | 06 Oct 26 |  |
| 2.1 | Provide order confirmation info to production | Order coordinator | 26 Sep 26 | 29 Sep 26 |  |
| 2.2 | Analyse 6–12 months prasadam purchases & volumes | DMTT data | 27 Sep 26 | 03 Oct 26 |  |
| 2.3 | Estimate weekly minimum & festival peaks | DMTT data | 02 Oct 26 | 06 Oct 26 | 2.2 |
| 2.4 | Department budgets (LLP, Culture Connect, online donors) | Mukunda Dasa | 29 Sep 26 | 04 Oct 26 |  |
| 3 | Product, costing & packaging |  | 28 Sep 26 | 12 Oct 26 |  |
| 3.1 | Propose budget & item list to production for samples | Mukunda Dasa | 28 Sep 26 | 30 Sep 26 |  |
| 3.2 | Identify more long-shelf-life products | Production lead | 28 Sep 26 | 04 Oct 26 |  |
| 3.3 | Samples & costing sheets (mass & premium) | Production lead | 01 Oct 26 | 08 Oct 26 | 3.1 |
| 3.4 | Pricing & gift tiers finalised | Mukunda Dasa | 06 Oct 26 | 09 Oct 26 | 3.3 |
| 3.5 | Packaging, stickers, catalogue, menu design | DMTT designer | 30 Sep 26 | 10 Oct 26 |  |
| 3.6 | Sample gift boxes assembled for pitching | Production lead | 08 Oct 26 | 12 Oct 26 | 3.3,3.5 |
| 4 | Resources |  | 26 Sep 26 | 15 Oct 26 |  |
| 4.1 | Hire additional production/order person | Production lead | 26 Sep 26 | 10 Oct 26 |  |
| 4.2 | Assign corporate sales representative | Mukunda Dasa | 29 Sep 26 | 03 Oct 26 |  |
| 4.3 | Seasonal staff plan for Dasara/Diwali | Production lead | 05 Oct 26 | 15 Oct 26 | 2.3 |
| 5 | Pilot: Dasara & Diwali |  | 10 Oct 26 | 30 Nov 26 |  |
| 5.1 | Owner meetings (companies, MNR, chambers, BNI) | Mukunda Dasa + sales rep | 10 Oct 26 | 31 Oct 26 | 3.6 |
| 5.2 | Serve the three companies that already asked | Sales rep | 10 Oct 26 | 18 Oct 26 | 3.6 |
| 5.3 | Mahalaya & Dasara stall roll-out | Production lead | 08 Oct 26 | 20 Oct 26 | 4.3 |
| 5.4 | Weekly internal standing orders live | Order coordinator | 12 Oct 26 | 19 Oct 26 | 2.3 |
| 5.5 | Diwali gift production & dispatch | Production lead | 20 Oct 26 | 06 Nov 26 | 5.1 |
| 5.6 | Sell leftovers online / Instagram | DMTT | 09 Nov 26 | 20 Nov 26 | 5.5 |
| 5.7 | Pilot review & lessons learned | Mukunda Dasa | 23 Nov 26 | 30 Nov 26 | 5.6 |
| 6 | Channel launch |  | 01 Dec 26 | 31 Mar 27 |  |
| 6.1 | Shelf-life lab tests & labels | Quality & compliance | 01 Dec 26 | 31 Dec 26 |  |
| 6.2 | Shopify store live | DMTT e-commerce | 01 Dec 26 | 15 Jan 27 | 6.1 |
| 6.3 | Amazon listing | E-commerce advisor | 05 Jan 27 | 31 Jan 27 | 6.2 |
| 6.4 | New Year, Vaikuntha Ekadashi & Sankranti campaigns | DMTT | 10 Dec 26 | 15 Jan 27 |  |
| 6.5 | Gated community stalls (10 → 30) | Sales rep | 10 Jan 27 | 31 Mar 27 |  |
| 6.6 | Catering pilot | Production lead | 15 Jan 27 | 31 Mar 27 |  |
| 6.7 | CRM + B2B sales executive | Mukunda Dasa | 01 Jan 27 | 15 Feb 27 |  |
| 6.8 | Subscription box beta | DMTT | 01 Feb 27 | 31 Mar 27 | 6.2 |
| 7 | Scale in Hyderabad |  | 01 Apr 27 | 30 Sep 27 |  |
| 7.1 | Pagoda costing, procurement & installation | Facilities | 01 Apr 27 | 30 Jun 27 |  |
| 7.2 | Pickles, papads, powders launch | Production lead | 15 Apr 27 | 30 Jun 27 | 6.1 |
| 7.3 | Learning visits: Mysore & Ahmedabad | Production lead | 15 Apr 27 | 15 May 27 |  |
| 7.4 | Janmashtami 2027 10× plan & execution | Mukunda Dasa + Production lead | 01 Jun 27 | 05 Sep 27 | 7.1 |
| 7.5 | Year-1 review & Year-2 budget | Mukunda Dasa | 10 Sep 27 | 30 Sep 27 | 7.4 |
| 8 | Year 2+: unit, QSR, exports |  | 01 Oct 27 | 30 Sep 28 |  |
| 8.1 | Dedicated production unit business case & build | Temple leadership | 01 Oct 27 | 31 Mar 28 | 7.5 |
| 8.2 | QSR brand licence & 1–3 pilots | Mukunda Dasa | 01 Oct 27 | 30 Jun 28 | 7.5 |
| 8.3 | Export readiness (IEC, APEDA, partners) | Mukunda Dasa | 01 Jan 28 | 30 Sep 28 | 8.1 |

# 7. Milestones

| Milestone | Target date | Gate criteria |
| --- | --- | --- |
| M1 Plan circulated | 30 Sep 2026 | Plan shared with production lead and manager |
| M2 Decision meeting / charter signed | 5 Oct 2026 | Products, quantities, budget, pricing agreed |
| M3 Sales kit ready | 12 Oct 2026 | Catalogue, prices, 10 sample boxes |
| M4 Dasara delivered | 20 Oct 2026 | Stalls live, first corporate orders delivered |
| M5 Diwali delivered | 6 Nov 2026 | All Diwali orders dispatched on time |
| M6 Pilot review | 30 Nov 2026 | P&L, ROI, lessons; go/no-go for Phase 2 |
| M7 Online store live | 15 Jan 2027 | Shopify live with ≥12 SKUs |
| M8 Pagodas installed | 30 Jun 2027 | Permanent stalls in place |
| M9 Janmashtami 2027 | Sep 2027 | Counter sales ≥ ₹30 L (base) / ₹60 L (stretch) |
| M10 Year-1 review | 30 Sep 2027 | Annual report and Year-2 budget approved |

# 8. Budget [ESTIMATE]

| Item | ₹ lakh (Y1) | Note |
| --- | --- | --- |
| Additional staff salaries | 24 | 1 order coordinator now + seasonal cooks + sales exec (Phase 2) |
| Marketing (ads, content, samples) | 12 | ≈5% of revenue |
| Packaging design & moulds | 3 | One-time catalogue, dies, stickers |
| Pagodas & stall kits | 6 | Rain-proof pagodas, tables, signage, POS |
| Technology (Shopify, apps, POS, CRM) | 3 | Subscriptions and integrations |
| Utilities & kitchen overheads (allocated) | 8 | Power, gas, water, maintenance |
| Compliance, testing, licences | 2 | Shelf-life tests, FSSAI, audits |
| Logistics not charged to customers | 5 | Free-shipping offers, B2B deliveries |
| Contingency | 4 | ≈5% |
| Total opex | 67 |  |

| Capex item | Estimate | When |
| --- | --- | --- |
| Small machines (chikki cutter, laddu maker, sealing, packing) | ₹8–15 L | Phase 2–3 |
| Permanent pagodas (8–12 units) | ₹6–12 L | Phase 3 |
| Storage racks, dehumidifier, weighing & labelling | ₹3–5 L | Phase 2 |
| Dedicated production unit fit-out | ₹50 L–1.5 Cr | Phase 4 (only after demand is proven) |
| Delivery vehicle | ₹8–12 L | Phase 3–4 |

# 9. Risk register

Likelihood (L) and impact (I) on a 1–5 scale; score = L × I. Scores of 15+ are reviewed weekly.

| ID | Risk | L | I | Score | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R-01 | Kitchen cannot meet Diwali peak volume | 4 | 5 | 20 | Forecast from order data; seasonal staff; cap orders by capacity; 50% advance; partner kitchens on standby | Production lead |
| R-02 | Premium-only pricing fails to cover fixed costs | 3 | 4 | 12 | Two-tier model; mass tier for volume; monthly margin review | Mukunda Dasa |
| R-03 | Food-safety incident harms temple reputation | 2 | 5 | 10 | FSSAI compliance, hygiene SOPs, batch codes, shelf-life tests, staff medical checks, recall plan | Quality |
| R-04 | Use of the ISKCON name on commercial packaging questioned | 3 | 4 | 12 | Written approval from temple leadership / group legal; consistent brand guidelines; consider a sub-brand | Sponsor |
| R-05 | Perception that prasadam is being commercialised | 3 | 3 | 9 | Passive selling, devotional messaging, transparent use of proceeds, prasadam offered first | Mukunda Dasa |
| R-06 | Ingredient price spikes (ghee, jaggery, nuts) | 4 | 3 | 12 | Forward-buy before season, two suppliers, sugar/jaggery flexibility, price validity clauses | Production lead |
| R-07 | Festival sales below plan; leftover stock | 3 | 3 | 9 | Shelf-stable SKUs, pre-orders, online/Instagram clearance | DMTT |
| R-08 | Late B2B deliveries during peak | 3 | 4 | 12 | Production calendar, cut-off dates, dispatch buffer, own vehicle | Order coordinator |
| R-09 | Staff overload across departments | 4 | 3 | 12 | Dedicated hires; clear RACI; hours tracked in DMTT | Prod. manager |
| R-10 | Online shipping damage/spoilage | 3 | 3 | 9 | Moisture-proof packs, tested courier partners, only shelf-stable items online | E-commerce advisor |
| R-11 | Rain disrupts festival stalls | 3 | 3 | 9 | Rain-proof pagodas; indoor fallback locations | Facilities |
| R-12 | Cash/stock leakage at stalls | 2 | 3 | 6 | UPI-first, POS, stock reconciliation per shift | Finance |
| R-13 | QSR partner quality not aligned with temple standards | 3 | 5 | 15 | Strict brand licence, audits, satvik SOPs, exit clauses | Sponsor |
| R-14 | Regulatory changes (FSSAI, GST) | 2 | 2 | 4 | Quarterly compliance review | Finance |

# 10. Quality management

Standard recipes and yield sheets for every SKU; taste panel sign-off before launch.

Shelf-life lab test per SKU and pack type before selling online.

Batch codes, MFD and best-before on every pack; FIFO in stores.

Hygiene SOP: head covers, gloves, hand-wash, pest control, cleaning log; staff medical checks.

Supplier checks for ghee, oil, jaggery, nuts; retain samples of each batch for 30 days.

Customer complaint log with 48-hour response and root-cause review.

Monthly internal audit; external FSSAI audit readiness.

# 11. Communication plan

| Audience | What | How |
| --- | --- | --- |
| Temple leadership | Monthly ROI report, quarterly steering deck | Email + meeting |
| Production team | Weekly production plan, festival forecasts | System + WhatsApp group |
| Internal departments | Order cut-offs, price list, delivery day | System notice |
| Corporate clients | Catalogue, quotes, order status | Email, WhatsApp |
| Donors & public | Festival campaigns, launches | WhatsApp, SMS, social, website |

# 12. Governance and reporting

| Cadence | Forum | Chair |
| --- | --- | --- |
| Daily (festival weeks) | Stand-up: production + stalls + dispatch | Production lead |
| Weekly | Order & pipeline review (orders, production plan, sales pipeline, issues) | Mukunda Dasa |
| Monthly | P&L and ROI review with DMTT & finance; KPI dashboard | Mukunda Dasa + Finance |
| After each hero campaign | Post-campaign review and lessons learned | Vertical lead |
| Quarterly | Steering review with temple leadership; budget and capex decisions | Sponsor |

## KPI dashboard

| KPI | Definition | Unit | Frequency |
| --- | --- | --- | --- |
| Revenue | Monthly gross revenue by stream | ₹ lakh | Monthly |
| Gross margin | Revenue minus ingredients, packaging, direct labour | % | Monthly |
| ROI | (Contribution − DMTT & marketing cost) ÷ total invested cost | % | Monthly |
| Hours invested | Hours spent by DMTT, production, sales on the vertical | hours | Weekly |
| Festival sales | Sales per festival and per stall-hour | ₹ | Per event |
| Corporate pipeline | Leads, meetings, proposals, POs, boxes | count | Weekly |
| Online | Orders, conversion rate, CAC, ROAS, repeat rate | various | Weekly |
| Operations | On-time delivery %, order fill rate, spoilage % | % | Weekly |
| Quality | Complaints per 1,000 orders; audit score | count / score | Monthly |
| Customer | Rating, NPS, repeat B2B clients | score | Quarterly |

## DMTT ROI tracking

Separate cost centre for the vertical in accounts.

Every order tagged by stream (R1–R14), channel and campaign.

Weekly time log by each team member working on the vertical.

Marketing spend tagged by campaign; ROAS per campaign.

Monthly P&L by stream and a one-page ROI summary for leadership.

## Decision and phase-gate flow

## DMTT ROI tracking flow

# 13. Change control

Any change to scope, budget above ₹1 lakh, pricing tiers or brand use is raised as a change request.

Project lead assesses impact on cost, time, capacity and risk within 3 working days.

Changes up to ₹5 lakh approved by project lead and production manager; above that by the sponsor.

Approved changes are logged in the tracker and communicated to all affected teams.

# 14. Issue and decision log

| Date | Decision / issue | By | Status |
| --- | --- | --- | --- |
| 26 Sep 2026 | Two price segments (mass + premium) will run together | Meeting | Agreed |
| 26 Sep 2026 | All prasadam orders go only to the internal production lead | Mukunda Dasa | Agreed |
| 26 Sep 2026 | Shelf life of 15–20 days is the first product criterion | Meeting | Agreed |
| 26 Sep 2026 | Sugar acceptable where jaggery is too costly | Meeting | Agreed |
| 26 Sep 2026 | Weekly minimum order with fixed delivery day | Meeting | Agreed |
| 26 Sep 2026 | Start with internal demand before external expansion | Meeting | Agreed |
| — | Brand name to use on packs | Sponsor | Open |
| — | Budgets per department | Mukunda Dasa | Open |

# 15. Action items

| # | Action | Owner | Due |
| --- | --- | --- | --- |
| A1 | Provide the order confirmation information requested for prasadam orders | Production team (order coordinator) | 29 Sep 2026 |
| A2 | Hire an additional person for prasadam production work | Production lead | 10 Oct 2026 |
| A3 | Propose available budget and requested items to production for samples and planning | Mukunda Dasa's team | 30 Sep 2026 |
| A4 | Analyse 6–12 months of prasadam purchases and order volumes; share regular and festival estimates | DMTT data | 3 Oct 2026 |
| A5 | Prepare and send the detailed plan for the prasadam and sweets vertical | Mukunda Dasa | 30 Sep 2026 (this document) |
| A6 | Identify additional prasadam products with longer shelf life | Production lead | 4 Oct 2026 |
| A7 | Prepare packaging and product presentation for bulk corporate gifting | DMTT designer + Production lead | 10 Oct 2026 |
| A8 | Send a representative to support meetings with large company owners | Mukunda Dasa | 3 Oct 2026 |
| A9 | Hold the finalisation meeting on products and quantities | Mukunda Dasa | 5 Oct 2026 |
| A10 | Route all prasadam orders only to the internal production lead | All departments | Immediate |
| A11 | Get pagoda costing done | Facilities | 31 Oct 2026 |
| A12 | Respond to the Chinmaya Mission 50,000-meal request | Mukunda Dasa | Immediate |

## Open questions

Final product list, quantities and weekly minimum per department?

Budget allocated for prasadam per department (LLP, Culture Connect, online donors)?

Pricing model split between premium and competitive tiers?

Real production capacity per day now, with one more hire, and at peak with seasonal staff?

Which infrastructure and staffing investments are justified before demand is validated?

Brand name on packs: 'ISKCON Hyderabad', 'Hare Krishna Golden Temple', or a sub-brand?

Which FSSAI licence covers commercial sale and e-commerce, and does it cover off-site stalls?

Transfer-pricing and profit-sharing between production and marketing teams?

Who owns catering for very large orders (50,000 meals) until a catering unit exists?