## Read me
Prasadam, Sweets & Savories Vertical – Project Tracker
Hare Krishna Golden Temple (ISKCON), Banjara Hills, Hyderabad
v1.0 draft, 26 September 2026
How to use
• WBS & Gantt: update Status and % done every week; the Gantt bars are drawn by formulas from Start/End.
• Risk register: Score = Likelihood × Impact (formula). 15+ is red, 8–14 amber.
• Financial model: yellow cells are inputs (blue text). Replace [ESTIMATE] numbers with the 6–12 month order data.
• KPI tracker and ROI log: fill monthly/weekly; ROI is calculated automatically.
• Action items: the 12 actions from the 26 Sep 2026 meeting.
Generated from src/content.py – edit there and run src/build_all.py to rebuild all documents.

## WBS & Gantt
ID | Task | Owner | Phase | Start | End | Days | Depends on | Deliverable | Status | % done | 21-Sep | 28-Sep | 05-Oct | 12-Oct | 19-Oct | 26-Oct | 02-Nov | 09-Nov | 16-Nov | 23-Nov | 30-Nov | 07-Dec | 14-Dec | 21-Dec | 28-Dec | 04-Jan | 11-Jan | 18-Jan | 25-Jan | 01-Feb | 08-Feb | 15-Feb | 22-Feb | 01-Mar | 08-Mar | 15-Mar | 22-Mar | 29-Mar | 05-Apr | 12-Apr | 19-Apr | 26-Apr | 03-May | 10-May | 17-May | 24-May | 31-May | 07-Jun | 14-Jun | 21-Jun | 28-Jun | 05-Jul | 12-Jul | 19-Jul | 26-Jul | 02-Aug | 09-Aug | 16-Aug | 23-Aug | 30-Aug | 06-Sep | 13-Sep | 20-Sep | 27-Sep
1 | Initiation & governance |  | Phase 0 | 2026-09-26 | 2026-10-10
1.1 | Send detailed vertical plan to stakeholders | Mukunda Dasa | Phase 0 | 2026-09-26 | 2026-09-30 |  |  | This plan | Not started | 0%
1.2 | Production lead reviews plan with his manager | Production lead | Phase 0 | 2026-09-30 | 2026-10-03 |  | 1.1 | Feedback | Not started | 0%
1.3 | Decision meeting (Mukunda Dasa, production lead, manager) | Mukunda Dasa | Phase 0 | 2026-10-05 | 2026-10-05 |  | 1.2 | Signed-off charter | Not started | 0%
1.4 | Set up DMTT cost centre and ROI tracker | DMTT / Finance | Phase 0 | 2026-09-29 | 2026-10-06 |  |  | ROI dashboard v1 | Not started | 0%
1.5 | Confirm brand-use approval and FSSAI scope | Quality & compliance | Phase 0 | 2026-09-29 | 2026-10-09 |  |  | Compliance note | Not started | 0%
2 | Demand & data |  | Phase 0 | 2026-09-26 | 2026-10-06
2.1 | Provide order confirmation info to production | Order coordinator | Phase 0 | 2026-09-26 | 2026-09-29 |  |  | Order sheet | Not started | 0%
2.2 | Analyse 6–12 months prasadam purchases & volumes | DMTT data | Phase 0 | 2026-09-27 | 2026-10-03 |  |  | Trend report | Not started | 0%
2.3 | Estimate weekly minimum & festival peaks | DMTT data | Phase 0 | 2026-10-02 | 2026-10-06 |  | 2.2 | Demand forecast | Not started | 0%
2.4 | Department budgets (LLP, Culture Connect, online donors) | Mukunda Dasa | Phase 0 | 2026-09-29 | 2026-10-04 |  |  | Budget sheet | Not started | 0%
3 | Product, costing & packaging |  | Phase 0 | 2026-09-28 | 2026-10-12
3.1 | Propose budget & item list to production for samples | Mukunda Dasa | Phase 0 | 2026-09-28 | 2026-09-30 |  |  | Sample request | Not started | 0%
3.2 | Identify more long-shelf-life products | Production lead | Phase 0 | 2026-09-28 | 2026-10-04 |  |  | Extended item list | Not started | 0%
3.3 | Samples & costing sheets (mass & premium) | Production lead | Phase 0 | 2026-10-01 | 2026-10-08 |  | 3.1 | Costing sheets | Not started | 0%
3.4 | Pricing & gift tiers finalised | Mukunda Dasa | Phase 0 | 2026-10-06 | 2026-10-09 |  | 3.3 | Price list | Not started | 0%
3.5 | Packaging, stickers, catalogue, menu design | DMTT designer | Phase 0 | 2026-09-30 | 2026-10-10 |  |  | Sales kit | Not started | 0%
3.6 | Sample gift boxes assembled for pitching | Production lead | Phase 0 | 2026-10-08 | 2026-10-12 |  | 3.3,3.5 | 10 sample boxes | Not started | 0%
4 | Resources |  | Phase 0 | 2026-09-26 | 2026-10-15
4.1 | Hire additional production/order person | Production lead | Phase 0 | 2026-09-26 | 2026-10-10 |  |  | New hire | Not started | 0%
4.2 | Assign corporate sales representative | Mukunda Dasa | Phase 0 | 2026-09-29 | 2026-10-03 |  |  | Named rep | Not started | 0%
4.3 | Seasonal staff plan for Dasara/Diwali | Production lead | Phase 0 | 2026-10-05 | 2026-10-15 |  | 2.3 | Staff roster | Not started | 0%
5 | Pilot: Dasara & Diwali |  | Phase 1 | 2026-10-10 | 2026-11-30
5.1 | Owner meetings (companies, MNR, chambers, BNI) | Mukunda Dasa + sales rep | Phase 1 | 2026-10-10 | 2026-10-31 |  | 3.6 | Meeting log, POs | Not started | 0%
5.2 | Serve the three companies that already asked | Sales rep | Phase 1 | 2026-10-10 | 2026-10-18 |  | 3.6 | 3 orders | Not started | 0%
5.3 | Mahalaya & Dasara stall roll-out | Production lead | Phase 1 | 2026-10-08 | 2026-10-20 |  | 4.3 | Stall sales report | Not started | 0%
5.4 | Weekly internal standing orders live | Order coordinator | Phase 1 | 2026-10-12 | 2026-10-19 |  | 2.3 | Weekly schedule | Not started | 0%
5.5 | Diwali gift production & dispatch | Production lead | Phase 1 | 2026-10-20 | 2026-11-06 |  | 5.1 | Delivered orders | Not started | 0%
5.6 | Sell leftovers online / Instagram | DMTT | Phase 1 | 2026-11-09 | 2026-11-20 |  | 5.5 | Clearance report | Not started | 0%
5.7 | Pilot review & lessons learned | Mukunda Dasa | Phase 1 | 2026-11-23 | 2026-11-30 |  | 5.6 | Review deck | Not started | 0%
6 | Channel launch |  | Phase 2 | 2026-12-01 | 2027-03-31
6.1 | Shelf-life lab tests & labels | Quality & compliance | Phase 2 | 2026-12-01 | 2026-12-31 |  |  | Test reports | Not started | 0%
6.2 | Shopify store live | DMTT e-commerce | Phase 2 | 2026-12-01 | 2027-01-15 |  | 6.1 | Live store | Not started | 0%
6.3 | Amazon listing | E-commerce advisor | Phase 2 | 2027-01-05 | 2027-01-31 |  | 6.2 | Live listing | Not started | 0%
6.4 | New Year, Vaikuntha Ekadashi & Sankranti campaigns | DMTT | Phase 2 | 2026-12-10 | 2027-01-15 |  |  | Campaign reports | Not started | 0%
6.5 | Gated community stalls (10 → 30) | Sales rep | Phase 2 | 2027-01-10 | 2027-03-31 |  |  | Event log | Not started | 0%
6.6 | Catering pilot | Production lead | Phase 2 | 2027-01-15 | 2027-03-31 |  |  | 5+ events | Not started | 0%
6.7 | CRM + B2B sales executive | Mukunda Dasa | Phase 2 | 2027-01-01 | 2027-02-15 |  |  | CRM live | Not started | 0%
6.8 | Subscription box beta | DMTT | Phase 2 | 2027-02-01 | 2027-03-31 |  | 6.2 | 100 subscribers | Not started | 0%
7 | Scale in Hyderabad |  | Phase 3 | 2027-04-01 | 2027-09-30
7.1 | Pagoda costing, procurement & installation | Facilities | Phase 3 | 2027-04-01 | 2027-06-30 |  |  | Pagodas installed | Not started | 0%
7.2 | Pickles, papads, powders launch | Production lead | Phase 3 | 2027-04-15 | 2027-06-30 |  | 6.1 | New SKUs | Not started | 0%
7.3 | Learning visits: Mysore & Ahmedabad | Production lead | Phase 3 | 2027-04-15 | 2027-05-15 |  |  | Visit report | Not started | 0%
7.4 | Janmashtami 2027 10× plan & execution | Mukunda Dasa + Production lead | Phase 3 | 2027-06-01 | 2027-09-05 |  | 7.1 | Festival report | Not started | 0%
7.5 | Year-1 review & Year-2 budget | Mukunda Dasa | Phase 3 | 2027-09-10 | 2027-09-30 |  | 7.4 | Annual report | Not started | 0%
8 | Year 2+: unit, QSR, exports |  | Phase 4 | 2027-10-01 | 2028-09-30
8.1 | Dedicated production unit business case & build | Temple leadership | Phase 4 | 2027-10-01 | 2028-03-31 |  | 7.5 | Unit live | Not started | 0%
8.2 | QSR brand licence & 1–3 pilots | Mukunda Dasa | Phase 4 | 2027-10-01 | 2028-06-30 |  | 7.5 | Pilot outlets | Not started | 0%
8.3 | Export readiness (IEC, APEDA, partners) | Mukunda Dasa | Phase 4 | 2028-01-01 | 2028-09-30 |  | 8.1 | First export order | Not started | 0%

## Milestones
Milestone | Target date | Gate criteria | Status
M1 Plan circulated | 30 Sep 2026 | Plan shared with production lead and manager
M2 Decision meeting / charter signed | 5 Oct 2026 | Products, quantities, budget, pricing agreed
M3 Sales kit ready | 12 Oct 2026 | Catalogue, prices, 10 sample boxes
M4 Dasara delivered | 20 Oct 2026 | Stalls live, first corporate orders delivered
M5 Diwali delivered | 6 Nov 2026 | All Diwali orders dispatched on time
M6 Pilot review | 30 Nov 2026 | P&L, ROI, lessons; go/no-go for Phase 2
M7 Online store live | 15 Jan 2027 | Shopify live with ≥12 SKUs
M8 Pagodas installed | 30 Jun 2027 | Permanent stalls in place
M9 Janmashtami 2027 | Sep 2027 | Counter sales ≥ ₹30 L (base) / ₹60 L (stretch)
M10 Year-1 review | 30 Sep 2027 | Annual report and Year-2 budget approved

## Action items
# | Action | Owner | Due | Status | Notes
A1 | Provide the order confirmation information requested for prasadam orders | Production team (order coordinator) | 29 Sep 2026 | Open
A2 | Hire an additional person for prasadam production work | Production lead | 10 Oct 2026 | Open
A3 | Propose available budget and requested items to production for samples and planning | Mukunda Dasa's team | 30 Sep 2026 | Open
A4 | Analyse 6–12 months of prasadam purchases and order volumes; share regular and festival estimates | DMTT data | 3 Oct 2026 | Open
A5 | Prepare and send the detailed plan for the prasadam and sweets vertical | Mukunda Dasa | 30 Sep 2026 (this document) | Open
A6 | Identify additional prasadam products with longer shelf life | Production lead | 4 Oct 2026 | Open
A7 | Prepare packaging and product presentation for bulk corporate gifting | DMTT designer + Production lead | 10 Oct 2026 | Open
A8 | Send a representative to support meetings with large company owners | Mukunda Dasa | 3 Oct 2026 | Open
A9 | Hold the finalisation meeting on products and quantities | Mukunda Dasa | 5 Oct 2026 | Open
A10 | Route all prasadam orders only to the internal production lead | All departments | Immediate | Open
A11 | Get pagoda costing done | Facilities | 31 Oct 2026 | Open
A12 | Respond to the Chinmaya Mission 50,000-meal request | Mukunda Dasa | Immediate | Open

## RACI
Activity | Sponsor | Mukunda Dasa | Production lead | Prod. manager | DMTT | Sales rep | Finance | Quality
Vertical strategy & budget | A | R | C | C | C | I | C | I
Product list, recipes, samples | I | C | R/A | C | I | I | I | C
Costing & pricing | I | A | R | C | C | C | C | I
Packaging & catalogue design | I | A | C | I | R | C | I | C
Corporate & white-label sales | I | A | C | I | C | R | I | I
Festival stalls | I | A | R | C | C | C | C | C
Internal weekly orders | I | A | R | I | C | I | C | I
E-commerce & logistics | I | A | C | I | R | I | C | I
Compliance (FSSAI, labels, hygiene) | I | C | R | C | I | I | I | A
ROI tracking & reporting | I | A | C | I | R | I | R | I
Hiring & staffing | I | C | R | A | I | I | C | I
Capex (pagodas, machines, unit) | A | R | C | C | I | I | C | C
R = Responsible · A = Accountable · C = Consulted · I = Informed

## Team & roles
Role | Person | Responsibility
Executive sponsor | Temple leadership | Approves budget, brand use and major decisions
Vertical lead – marketing, sales & technology | Mukunda Dasa | Vision, network, marketing, e-commerce, DMTT reporting
Production lead | Prabhu (production) | Recipes, costing, samples, capacity, kitchen team
Production manager (reporting line) | Production lead's manager | Approves production commitments and resources
E-commerce & logistics advisor | Subhadra Radha Devi Mataji | Shopify/Amazon, fastest shipping
Corporate sales representative | To be assigned by Mukunda Dasa | Joins owner meetings; manages B2B pipeline
Order coordinator (new hire) | To hire now | Order confirmations, internal orders, production calendar
Design & packaging | DMTT designer | Catalogue, boxes, stickers, white-label mock-ups
Data & AI | DMTT data scientists | Demand analysis, targeting, ROI dashboard
Finance | Accounts team | Cost centre, GST, P&L, ROI
Quality & compliance | To assign | FSSAI, labelling, hygiene audits

## Risk register
ID | Risk | Likelihood (1-5) | Impact (1-5) | Score | Mitigation | Owner | Status
R-01 | Kitchen cannot meet Diwali peak volume | 4 | 5 |  | Forecast from order data; seasonal staff; cap orders by capacity; 50% advance; partner kitchens on standby | Production lead | Open
R-02 | Premium-only pricing fails to cover fixed costs | 3 | 4 |  | Two-tier model; mass tier for volume; monthly margin review | Mukunda Dasa | Open
R-03 | Food-safety incident harms temple reputation | 2 | 5 |  | FSSAI compliance, hygiene SOPs, batch codes, shelf-life tests, staff medical checks, recall plan | Quality | Open
R-04 | Use of the ISKCON name on commercial packaging questioned | 3 | 4 |  | Written approval from temple leadership / group legal; consistent brand guidelines; consider a sub-brand | Sponsor | Open
R-05 | Perception that prasadam is being commercialised | 3 | 3 |  | Passive selling, devotional messaging, transparent use of proceeds, prasadam offered first | Mukunda Dasa | Open
R-06 | Ingredient price spikes (ghee, jaggery, nuts) | 4 | 3 |  | Forward-buy before season, two suppliers, sugar/jaggery flexibility, price validity clauses | Production lead | Open
R-07 | Festival sales below plan; leftover stock | 3 | 3 |  | Shelf-stable SKUs, pre-orders, online/Instagram clearance | DMTT | Open
R-08 | Late B2B deliveries during peak | 3 | 4 |  | Production calendar, cut-off dates, dispatch buffer, own vehicle | Order coordinator | Open
R-09 | Staff overload across departments | 4 | 3 |  | Dedicated hires; clear RACI; hours tracked in DMTT | Prod. manager | Open
R-10 | Online shipping damage/spoilage | 3 | 3 |  | Moisture-proof packs, tested courier partners, only shelf-stable items online | E-commerce advisor | Open
R-11 | Rain disrupts festival stalls | 3 | 3 |  | Rain-proof pagodas; indoor fallback locations | Facilities | Open
R-12 | Cash/stock leakage at stalls | 2 | 3 |  | UPI-first, POS, stock reconciliation per shift | Finance | Open
R-13 | QSR partner quality not aligned with temple standards | 3 | 5 |  | Strict brand licence, audits, satvik SOPs, exit clauses | Sponsor | Open
R-14 | Regulatory changes (FSSAI, GST) | 2 | 2 |  | Quarterly compliance review | Finance | Open

## Financial model
All figures ₹ lakh. Yellow cells = inputs [ESTIMATE]. Replace with real order data.
Revenue stream | Year 1 | Y2 growth × | Year 2 | Y3 growth × | Year 3 | Gross margin % | Y1 gross profit | Basis
Internal supply (R1) | 36 | 1.3 |  | 1.2 |  | 25% |  | ₹3 L/month average across departments
Festival stalls (R2) | 45 | 1.8 |  | 1.5 |  | 50% |  | Janmashtami 2027 ₹30 L (5× first year) + other festivals ₹15 L
Restaurant & lawn uplift (R3) | 18 | 1.5 |  | 1.4 |  | 35% |  | Incremental ₹1.5 L/month
Corporate gifting – own brand (R4) | 30 | 2.2 |  | 1.8 |  | 40% |  | Diwali/Dasara 5,000 boxes × ₹450 + New Year/Sankranti
White-label gifting (R5) | 12 | 2.5 |  | 1.8 |  | 40% |  | 8–10 clients
Daily snacking retail (R6) | 15 | 1.8 |  | 1.6 |  | 40% |  | Top-10 SKUs via shop and counters
E-commerce (R7) | 18 | 3 |  | 2 |  | 30% |  | Ramp ₹0.5 L → ₹3 L/month
Catering & bulk meals (R8) | 20 | 2.5 |  | 2 |  | 25% |  | Events + 1 large order
Gated communities (R9) | 10 | 2 |  | 1.5 |  | 40% |  | 10→30 communities, ₹12k–₹15k per event
Outbound B2B & life events (R10) | 8 | 2.5 |  | 2 |  | 35% |  | Sales executive from Phase 2
Pickles, papads, powders (R11) | 4 | 3 |  | 2 |  | 40% |  | Launch Phase 3
Donor & sponsor packs (R14) | 8 | 1.5 |  | 1.3 |  | 35% |  | Bahumana, monsoon tins
QSR royalty (R12) | 0 | 0 |  | 0 |  | 100% |  | Year 2 pilots; Year 3 royalty modelled separately
Total revenue
Year-1 incremental operating costs | ₹ lakh | Note
Additional staff salaries | 24 | 1 order coordinator now + seasonal cooks + sales exec (Phase 2)
Marketing (ads, content, samples) | 12 | ≈5% of revenue
Packaging design & moulds | 3 | One-time catalogue, dies, stickers
Pagodas & stall kits | 6 | Rain-proof pagodas, tables, signage, POS
Technology (Shopify, apps, POS, CRM) | 3 | Subscriptions and integrations
Utilities & kitchen overheads (allocated) | 8 | Power, gas, water, maintenance
Compliance, testing, licences | 2 | Shelf-life tests, FSSAI, audits
Logistics not charged to customers | 5 | Free-shipping offers, B2B deliveries
Contingency | 4 | ≈5%
Total opex
Year-1 summary | ₹ lakh
Gross revenue
Gross profit
Operating costs
Net contribution (before capex)
Net margin %
Capex item | Estimate | When
Small machines (chikki cutter, laddu maker, sealing, packing) | ₹8–15 L | Phase 2–3
Permanent pagodas (8–12 units) | ₹6–12 L | Phase 3
Storage racks, dehumidifier, weighing & labelling | ₹3–5 L | Phase 2
Dedicated production unit fit-out | ₹50 L–1.5 Cr | Phase 4 (only after demand is proven)
Delivery vehicle | ₹8–12 L | Phase 3–4

## Unit economics
Item | MRP ₹ (incl. 5% GST) | Net of GST | Ingredients | Packaging | Labour & overhead | Gross profit | GM %
Seva box (₹350) | 350 |  | 140 | 35 | 50
Utsav box (₹900) | 900 |  | 360 | 90 | 110
Vaikuntha box (₹2,000) | 2000 |  | 850 | 300 | 200
Chikki 200 g (₹80) | 80 |  | 32 | 8 | 12
Namkeen 500 g (₹180) | 180 |  | 75 | 12 | 25
Festival combo (₹200) | 200 |  | 80 | 12 | 28

## KPI tracker
KPI | Definition | Unit | Frequency | Target | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27 | May-27 | Jun-27 | Jul-27 | Aug-27 | Sep-27
Revenue | Monthly gross revenue by stream | ₹ lakh | Monthly
Gross margin | Revenue minus ingredients, packaging, direct labour | % | Monthly
ROI | (Contribution − DMTT & marketing cost) ÷ total invested cost | % | Monthly
Hours invested | Hours spent by DMTT, production, sales on the vertical | hours | Weekly
Festival sales | Sales per festival and per stall-hour | ₹ | Per event
Corporate pipeline | Leads, meetings, proposals, POs, boxes | count | Weekly
Online | Orders, conversion rate, CAC, ROAS, repeat rate | various | Weekly
Operations | On-time delivery %, order fill rate, spoilage % | % | Weekly
Quality | Complaints per 1,000 orders; audit score | count / score | Monthly
Customer | Rating, NPS, repeat B2B clients | score | Quarterly

## ROI & hours log
Month | Stream (R1–R14) | Revenue ₹ | Ingredients ₹ | Packaging ₹ | Direct labour ₹ | Marketing ₹ | Overheads ₹ | DMTT hours | Production hours | Sales hours | Hourly cost ₹ | Value of hours ₹ | Contribution ₹ | ROI %

## Revenue streams
ID | Stream | What | Why | How | Phase | Capex | Margin | KPIs
R1 | Internal supply to departments | Weekly standing orders to Culture Connect, LLP, online donors dispatch, corporate relations and campaigns, with one fixed delivery day and festival top-ups. | Guaranteed base load for the kitchen from day one; replaces outside vendors. | Order-trend analysis (6–12 months) → minimum weekly quantity per department → internal price list → order form in the system. | Phase 0–1 | Low | Low–Medium | Weekly order fulfilment %, on-time %, internal cost saved vs outside vendors
R2 | Festival stalls and counters | Rows of stalls at high-footfall points on festival days; permanent rain-proof pagodas; restaurant takes the entire lawn. | Proven: Janmashtami 2026 sold out at ≈₹6 lakh with limited counters. Target 10×. | Footfall map → stall layout (entrance, exit queue, Goshala path, staircases, garden, waterfall, Samskara) → UPI + POS → stock plan from calendar → leftovers go online. | Phase 1 onward | Medium (pagodas) | High | Sales per festival, sales per stall per hour, stock-out time, leftover %
R3 | Temple restaurant and lawn food court | Restaurant as the daily anchor; on festival days full-length counters, chairs and round tables across the lawn. | Captures every visitor; 365-day revenue. | Menu engineering, QR ordering, festival lawn SOP, rental furniture contracts. | Phase 1–3 | Medium | Medium | Daily covers, average bill, festival-day revenue
R4 | Corporate gifting (own brand) | Dasara, Diwali, New Year, Sankranti and other gift boxes in three tiers, with dry fruits and sweets; samples, menu, price list. | About 58% of Diwali gifting is corporate; our network reaches owners directly; three companies have already asked. | Gift catalogue + samples → owner meetings (Mukunda Dasa with production rep) → PO with 50% advance → production calendar → dispatch. | Phase 1 onward | Low (packaging) | High | Boxes sold, average order value, repeat clients, advance collected
R5 | White-label / co-branded gifting | Same boxes with the client's logo and message (sticker or printed sleeve), so their brand travels with our prasadam. | Companies are already paying some vendor; the owner prefers a trusted source. | Brand-sticker template, MOQ per design, proof approval, 10–15 day lead time. | Phase 1 onward | Low | High | White-label orders, lead time, design approval cycle
R6 | Daily snacking (365-day retail) | Sweets and savories unconnected to festivals: chikkis, kaja, khara, namkeen, puri unde, laddus, 250 g weekly specials. | Evergreen demand; rotation keeps the kitchen busy. | Top-10 SKU list, standard pack sizes, shelf-life testing, temple shop + restaurant + online. | Phase 1–2 | Low | Medium | Units per SKU per week, sell-through, returns/spoilage
R7 | E-commerce (own store + marketplaces) | Shopify store and Amazon listing for shelf-stable items, pan-India shipping, subscriptions, donor bundles. | Scale through technology; reuse donor dispatch and Amazon experience (≈15,000 parcels). | Catalogue & photography → Shopify + payment + courier aggregator → Amazon → ads funnel → WhatsApp retargeting. | Phase 2 | Low | Medium | Orders/month, CAC, ROAS, repeat rate, delivery TAT
R8 | Catering and bulk meals | Satvik catering for house programmes, life events, corporate and institutional events; bulk meal packets (e.g. 50,000 meals). | Strong demand; many requests already; high visibility for the brand. | Start with drop-off catering from existing kitchen; partner kitchens for very large orders; later dedicated catering unit. | Phase 2–4 | High (at scale) | Medium | Events/month, plates served, per-plate margin, feedback score
R9 | Gated community flea markets | Weekend stalls in ~100 gated communities, pre-orders for festivals, community WhatsApp groups. | Access already exists; organisers have given free stalls. | Mobile stall kit, 2-person team, route calendar, lead capture for donor/preaching programmes. | Phase 2 | Low | Medium | Events/month, sales/event, leads captured
R10 | Outbound B2B and life-event sales | Sell to companies, event managers and families for openings, naming ceremonies, birthdays, weddings, vehicle pujas. | The open 'public circle' beyond our own contacts. | Sales executive, CRM pipeline, Google Ads for 'satvik catering Hyderabad', referral fees for event planners. | Phase 2–3 | Low | Medium | Leads, conversion %, revenue per salesperson
R11 | Pickles, papads and powders | Masala powders, sambar powder, pickles, papads: very long shelf life, ideal for online and export. | Adjacent vertical with low spoilage; strong Andhra/Telangana demand. | Recipe standardisation, lab testing, FSSAI labelling, co-packer if needed. | Phase 3 | Low–Medium | Medium–High | SKUs live, online share, export enquiries
R12 | QSR and fine-dine restaurants | Satvik quick-service outlets under the brand via the interested franchise partner; vision of 100 QSRs in Hyderabad; later fine dine. | Partner offers network, funds and execution; pure-veg QSR is under-served. | Brand licence agreement, central kitchen, 1–3 pilot outlets, SOPs, then scale. | Phase 4–5 | Partner-funded | Royalty 4–8% [ESTIMATE] | Outlets live, royalty income, food-safety audit scores
R13 | Exports and diaspora | Long-shelf-life range for diaspora markets and temples abroad. | Family business in Malaysia; European contacts; ISKCON global network. | Central FSSAI licence + IEC + APEDA; export partner; destination-country labelling. | Phase 5 | Medium | Medium–High | Countries served, export revenue
R14 | Donor and sponsor packs | Bahumana gift boxes for big donors, sponsor prasadam for festivals, 5 kg namkeen tins in monsoon. | Deepens donor relationships; big donors already ask. | Donor-care team offers packs with campaigns; sponsorship tiers include prasadam. | Phase 1 onward | Low | Medium | Packs sent, donor retention uplift

## Audiences
Audience | Circle | Who | Needs | Offer | Channel | Price
Temple visitors and festival crowds | Circle 1: those who come to us | Daily visitors, weekend families, festival crowds (Janmashtami, Mahalaya, Ratha Yatra, Gaura Purnima, etc.) | Quick purchase, prasadam to take home, meals on the lawn | Restaurant, lawn food court, multiple festival stalls, take-home packs, 250 g see-through boxes | Stalls at entrance/exit/Goshala path, restaurant, QR menus, UPI | Mass tier ₹30–₹250
Donors and life members | Circle 1: those who come to us | Online donors across India, big donors, sponsors, Virpaksha daily donors | Blessed prasadam at home; gifts for family and staff | Donor prasadam packs, bahumana boxes, 5 kg namkeen tins, festival hampers | Existing donor dispatch system, WhatsApp, donor-care calls | Mid to premium
Internal departments | Circle 1: those who come to us | Culture Connect, LLP, online donor team, corporate relations, campaigns | Reliable weekly supply at an agreed rate | Weekly standing order, one fixed delivery day, festival top-ups | Internal order form in the system; monthly budget per department | Internal transfer price (cost + agreed margin)
Corporate companies | Circle 2: those we go to (B2B) | Owners/HR/admin of firms with 500–10,000+ staff (steel, IT, pharma, real estate, T-Hub startups) | Festival gifts for staff and clients, on time, branded, within budget | Own-brand gift boxes (3 tiers) and white-label boxes with company branding; samples, menu, price list | Owner-level meetings (Mukunda Dasa + production rep), chamber and BNI referrals, LinkedIn, email | ₹250–₹2,500 per box; volume slabs
Educational institutions | Circle 2: those we go to (B2B) | MNR group (42 institutions) and other school/college chains | Gifts for staff and students; event snacks | Low-ticket student packs, staff boxes, event catering | Chairman relationships; academic-calendar planning | Mass tier with bulk slabs
Associations and professional networks | Circle 2: those we go to (B2B) | Telangana Chamber of Commerce, BNI, Rotary, Round Table, Alpha Circle, ICSI/ICAI Hyderabad chapters | Member gifts, event hampers, meeting snacks | Co-branded hampers, member discount codes, event snack boxes | Presidents/secretaries, chapter meetings, newsletters | Mid tier
Event management companies | Circle 2: those we go to (B2B) | Firms running Dandiya, weddings, corporate events (e.g. Naukaran Entertainment) | Return gifts, event food counters | Return-gift boxes, live counters, catering | Partner commission / referral fee | Mid tier
Gated communities | Circle 3: open public (B2C outside) | ~100 gated communities with weekend flea markets | Tasty, pure snacks; festival supplies | Weekend stall with top sellers, pre-order for festivals, community WhatsApp group | Flea-market organisers (free stalls offered before), RWA committees | Mass tier
Life-event families (open circle) | Circle 3: open public (B2C outside) | Families holding house-warming, naming ceremony, birthdays, weddings, car/vehicle puja, shop openings, shraddha | Prasadam packs, return gifts, satvik catering | Occasion packs, catering menus, bulk sweets | Google Ads, Instagram, referrals, temple ceremony desk | Mid tier
Online shoppers across India | Circle 4: digital | Social-media followers, NRIs sending gifts home, health-conscious buyers | Trusted, pure, shelf-stable sweets delivered fast | Shopify store + Amazon; subscriptions; diabetic-friendly namkeen; jaggery range | Meta Ads, Google Ads, WhatsApp, RCS, SMS, SEO, influencers | Mid tier + shipping
Health-conscious and diabetic buyers | Circle 4: digital | Buyers avoiding refined sugar, chemicals and colours | Jaggery-based, low-sugar, millet, poha puffed rice | 'Satvik Wellness' sub-range; namkeen for diabetics | Content marketing, doctors/yoga communities | Premium
Institutional bulk / large gatherings | Circle 5: scale | Spiritual/cultural organisations (e.g. Chinmaya Mission 50,000 meals), government and corporate events | Very large volumes, on time, hygienic | Bulk meal packets, prasadam packs, catering | Direct leadership contact; tender responses | Per-plate contract
QSR and restaurant diners | Circle 5: scale | Urban young families and office-goers wanting pure veg fast food | Fast, affordable, pure veg | Satvik QSR outlets (franchise with partner), later fine dine | Franchise partner, food-delivery apps | ₹99–₹399 meals
Export and diaspora | Circle 5: scale | Indian diaspora (Malaysia, Europe, USA, Middle East), ISKCON temples abroad, Indian grocery stores | Authentic long-shelf-life sweets, pickles, powders | Export-grade packaged range | Family business in Malaysia, European contacts, APEDA, Amazon Global | Export pricing

## Products
Product | Category | Shelf life (days) | Tier | Sweetener | Pack sizes | Notes
Groundnut chikki | Sweet – brittle | 60–90 | Mass | Jaggery | 100 g, 200 g, 500 g | Top shelf-life item; ideal for online and gifting
Til chikki (black & white) | Sweet – brittle | 60–90 | Mass/Premium | Jaggery | 100 g, 200 g | Sankranti hero product
Dry-fruit chikki | Sweet – brittle | 45–60 | Premium | Jaggery/Sugar | 200 g, gift tin | Corporate gifting
Puri unde (puffed-rice balls) | Sweet – laddu | 20–30 | Mass | Jaggery, coconut, elaichi | 6-pc, 12-pc | Karnataka favourite; light, healthy
Poha puffed-rice unde | Sweet – laddu | 20–30 | Wellness | Jaggery | 6-pc | For health-conscious buyers
Kaja / square kaja | Sweet – fried | 15–20 | Mass | Sugar syrup | 250 g, 500 g | Andhra classic
Besan / boondi laddu | Sweet – laddu | 10–15 | Mass/Premium | Sugar, ghee | 250 g, 500 g, 1 kg | Festival and temple staple
Dry-fruit laddu | Sweet – laddu | 20–30 | Premium | Dates/jaggery | 250 g, gift box | No added sugar option
Mysore pak | Sweet – ghee | 15–20 | Premium | Sugar, ghee | 250 g, 500 g | Gift box star
Khara / mixture namkeen | Savory | 30–45 | Mass | — | 200 g, 500 g, 5 kg tin | Diabetic-friendly choice
Chakli / murukku | Savory | 30–45 | Mass | — | 200 g, 400 g | All-season
Ribbon pakoda / chekkalu | Savory | 30–45 | Mass | — | 200 g | Telangana favourite
Roasted/spiced nuts | Savory | 60–90 | Premium | — | 150 g tins | Gift boxes
Masala powders & sambar powder | Pantry | 180+ | Mid | — | 100 g, 250 g | Pickles/powders vertical
Pickles | Pantry | 180+ | Mid | — | 250 g, 500 g | Satvik (no onion/garlic) differentiator
Papads | Pantry | 180+ | Mass | — | 200 g | Long shelf life
Dry fruits assortment | Gifting | 90+ | Premium | — | Gift boxes | Wooden box option
Weekly special (250 g box) | Rotating | 7–20 | Mass | Varies | 250 g see-through | Already tested with very good response

## Gift tiers
Tier | Price | Contents | Best for
Seva box | ₹250–₹450 | 3 items (chikki, namkeen, laddu) in a see-through or card box with brand sticker | Staff gifting at scale, students, communities
Utsav box | ₹600–₹1,200 | 5–6 items including a premium sweet and dry fruits in a printed rigid box | Employees, association members, donors
Vaikuntha box | ₹1,500–₹3,000+ | Wooden box, dry fruits, premium sweets, small Deity picture / Gita card | Clients, VIPs, directors, big donors
White-label add-on | +₹15–₹60 per box | Client logo sticker/sleeve, greeting card, custom message | Any tier, MOQ applies

## Festival calendar
Festival | When (approx.) | Opportunity | Demand | Forecast qty | Staff needed | Owner
Mahalaya / Pitru Paksha | 26 Sep – 10 Oct 2026 | Stalls for devotees doing service; prasadam packs | Medium
Navaratri & Dasara (Vijayadashami) | 11 – 20 Oct 2026 | Corporate & institution gifting, Dandiya tie-ups | Very high
Deepavali | 8 Nov 2026 | Gift boxes, white-label, donors | Very high
Kartika month / Damodara | Oct – Nov 2026 | Lamp-offering visitors; stalls | High
Gita Jayanti | Dec 2026 | Gita + prasadam gift packs | Medium
New Year | 1 Jan 2027 | Corporate new-year gifting | High
Vaikuntha Ekadashi | Dec 2026 / Jan 2027 | Huge footfall; stalls | Very high
Makara Sankranti | 14 Jan 2027 | Til chikki, sweets, gifting | High
Gaura Purnima / Holi | Mar 2027 | Stalls, festival feast | Medium
Ugadi & Sri Rama Navami | Mar – Apr 2027 | Ugadi packs, gifting | Medium
Narasimha Chaturdashi | May 2027 | Stalls | Medium
Ratha Yatra | Jun – Jul 2027 | Street stalls along the route | High
Sri Krishna Janmashtami | Aug/Sep 2027 | 10× target on counters, online pre-orders | Very high
Ganesh Chaturthi | Sep 2027 | Laddu/modak demand, gifting | High

## Business ideas
Idea | Description | Priority | Owner | Test by
Satvik Subscription Box | Monthly box of 4–6 seasonal sweets and savories delivered to homes and offices; donor-exclusive pricing.
Festival Pre-order App/Page | Pre-book Janmashtami/Diwali boxes online; pick up at a dedicated counter to avoid queues; stock planned from pre-orders.
Corporate 'Prasadam Friday' | Weekly snack trays for company pantries on a subscription contract.
Student and hostel packs | Low-ticket packs for MNR and other institutions during exams and festivals.
Diabetic-friendly namkeen line | Clearly labelled low-sugar/no-sugar range for donors who cannot eat sweets.
Jaggery & millet wellness range | Premium health range (jaggery chikki, millet laddu, poha puffed-rice unde).
Occasion kits | House-warming, naming ceremony, vehicle puja, shraddha and wedding return-gift kits.
Monsoon namkeen tins | 5 kg tins for big donors and showrooms in the rainy season.
World-record event | Largest laddu / largest chikki / most prasadam packets in a day for PR (India Book of Records).
Live-kitchen experiences | Weekend 'make your own laddu' workshops for families and corporate teams.
Temple-to-desk vending | Branded shelf-stable snack racks in corporate offices and co-working spaces.
Instagram flash sales | Clear post-festival leftover stock with limited-time offers.
Referral programme for event planners | Commission for every catering or return-gift order referred.
Sponsor-a-box | Donors sponsor prasadam boxes distributed to the needy on festivals (cause marketing).
Travelling prasadam (Yatra tie-in) | Shelf-stable packs for yatris on the temple's pilgrimage tours (links to the Yatra department).
NRI gifting portal | Order from abroad, delivered to family in India for festivals.

## Open questions
Question | Owner | Answer | Date
Final product list, quantities and weekly minimum per department?
Budget allocated for prasadam per department (LLP, Culture Connect, online donors)?
Pricing model split between premium and competitive tiers?
Real production capacity per day now, with one more hire, and at peak with seasonal staff?
Which infrastructure and staffing investments are justified before demand is validated?
Brand name on packs: 'ISKCON Hyderabad', 'Hare Krishna Golden Temple', or a sub-brand?
Which FSSAI licence covers commercial sale and e-commerce, and does it cover off-site stalls?
Transfer-pricing and profit-sharing between production and marketing teams?
Who owns catering for very large orders (50,000 meals) until a catering unit exists?

## Market research
Topic | Finding | Source | URL
India packaged sweets market | ₹8,431 crore in 2025, forecast ₹30,506 crore by 2034 (≈16% CAGR). Boxes are the largest packaging format (49%). | IMARC Group | https://www.imarcgroup.com/india-packaged-sweets-market
India namkeen market | Expected to grow by USD 4.89 billion between 2025 and 2030 at ≈10.2% CAGR; Tier-II/III retail expansion is a driver. | Technavio | https://www.technavio.com/report/namkeen-market-industry-in-india-analysis
Corporate gifting | India's corporate gifting market could cross ₹27,000 crore by 2030, with organised players taking nearly half. | Chococraft industry note | https://www.chococraft.in/blogs/corporate-gifts/corporate-gifting-industry-india-2025-2030
Diwali gifting mix | About 58% of Diwali gifts in 2025 were for corporate celebrations and 42% personal. | Outlook India / MyFlowerTree report | https://www.outlookindia.com/xhub/featured-insights/diwali-gifting-report-2025-what-india-is-really-buying-for-the-festival-of-lights
Premiumisation | Consumers increasingly prefer premium packaged sweets, curated hampers and customised assortments. | Mordor Intelligence | https://www.mordorintelligence.com/industry-reports/india-sweets-market
GST 2.0 | From 22 Sept 2025, pre-packaged and labelled namkeen, bhujia and mixtures moved from 12% to 5% GST; sweets are at 5%. Lower tax helps the mass segment. | Upstox / GST Council 56th meeting | https://upstox.com/news/personal-finance/latest-updates/gst-rate-cut-2025-namkeens-bhujia-and-other-pre-packaged-and-labelled-goods-to-get-cheaper-from-september-22/article-180743/
FSSAI licence thresholds | From 1 April 2026 Basic Registration covers turnover up to ₹1.5 crore (was ₹12 lakh); Central Licence threshold raised from ₹20 crore to ₹50 crore; State Licence in between. | Mondaq / FSSAI order of 13 March 2026 | https://www.mondaq.com/india/food-and-drugs-law/1801924/fssai-raises-turnover-limits-for-food-business-registration-and-licensing
Labelling | Pre-packaged sweets must show date of manufacture and best-before date. The best-before display for loose sweets on trays is now voluntary (recommended anyway). | FSSAI / Free Press Journal | https://www.freepressjournal.in/mumbai/fssai-removes-mandatory-best-before-date-requirement-for-non-packaged-sweets-fda-to-intensify-festival-season-inspections
Temple precedent | ISKCON Govinda's (Bangalore) runs an online store with same-day delivery slots for sweets, snacks, bakery, thalis and catering. | iskcongovindas.in | https://iskcongovindas.in/
Local competition | Hyderabad incumbents: G Pulla Reddy (since 1948, pure ghee, gifting page), Almond House (ships worldwide), Vellanki Foods, Dadu's, Pista House, Olive Mithai, Godavari Vantillu. | Brand sites / IndiaShopping | https://indiashopping.io/blogs/route-to-roots/famous-sweet-shops-in-hyderabad